## SCC List
Standard Cost Categories for Small Starts Projects
(Rev.21, June 2019)
10 GUIDEWAY & TRACK ELEMENTS (route miles)
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure
10.05 | Guideway: Built-up fill
10.06 | Guideway: Underground cut & cover
10.07 | Guideway: Underground tunnel
10.08 | Guideway: Retained cut or fill
10.09 | Track: Direct fixation
10.1 | Track: Embedded
10.11 | Track: Ballasted
10.12 | Track: Special (switches, turnouts)
10.13 | Track: Vibration and noise dampening
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform
20.03 | Underground station, stop, shelter, mall, terminal, platform
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development
20.06 | Automobile parking multi-story structure
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility
30.03 | Heavy Maintenance Facility
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track
40 SITEWORK & SPECIAL CONDITIONS
40.01 | Demolition, Clearing, Earthwork
40.02 | Site Utilities, Utility Relocation
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping
40.07 | Automobile, bus, van accessways including roads, parking lots
40.08 | Temporary Facilities and other indirect costs during construction
50 SYSTEMS
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications
50.06 | Fare collection system and equipment
50.07 | Central Control
60 ROW, LAND, EXISTING IMPROVEMENTS
60.01 | Purchase or lease of real estate
60.02 | Relocation of existing households and businesses
70 VEHICLES (number)
70.01 | Light Rail
70.02 | Heavy Rail
70.03 | Commuter Rail
70.04 | Bus
70.05 | Other
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
80.01 | Project Development
80.02 | Engineering (not applicable to Small Starts)
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Professional Liability and other Non-Construction Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up
90 UNALLOCATED CONTINGENCY
100 FINANCE CHARGES

## SCC Definitions
Standard Cost Categories for Small Starts Projects D E F I N I T I O N S |  | NOTE: The SCC cost breakdown is based on a traditional Design Bid Build model. If your project is Design Build, to the best of your ability, separate construction costs from design, administration, testing, etc. Put all construction costs in 10 through 50. Put design, administration, testing, etc. in 80 Professional Services.
(Rev.21, June 2019) |  | Please note that 'green' shaded areas are locked by FTA and cannot be updated. Only 'white' cells within the body of the worksheets (i.e., not outside the end of the worksheet) should be used to enter project data. DO NOT alter the SCC workbook to create additional worksheets, without first speaking with FTA staff.
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | Include guideway and track costs for all transit modes (heavy rail, light rail, commuter rail, BRT, rapid bus, bus, monorail, cable car, etc.) The unit of measure is route miles of guideway, regardless of width. As associated with the guideway, include costs for rough grading, excavation, and concrete base for guideway where applicable. Include all construction materials and labor regardless of whom is performing the work. For example, if the project is constructing guideway 2 miles in one direction and 2 miles in the opposite direction, it should be noted as "2" miles in SCC 10, and the cost of constructing the guideway should be noted in its entirety. In your written description of the scope, and in supporting graphic diagrams, indicate whether busway or rail track is single, double, triple, relocated, etc. Put guideway and track elements associated with yards in 30 Support Facilities below.
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure | Include foundation excavation; guideway structures including caissons, columns, bridges, viaducts, cross-overs, fly-overs.
10.05 | Guideway: Built-up fill | Include construction of earthen berms.
10.06 | Guideway: Underground cut & cover | Include excavation, retaining walls, backfill, underground guideway structure and finishes.
10.07 | Guideway: Underground tunnel | Include tunneling by means of a tunnel boring machine, drill blasting, mining, and immersed tube tunneling; tunnel structure and finishes.
10.08 | Guideway: Retained cut or fill | Include excavation, retaining walls, backfill, underground guideway structure and finishes.
10.09 | Track: Direct fixation | Include rails, connectors.
10.1 | Track: Embedded | Include rails, ties; ballast where applicable
10.11 | Track: Ballasted | Include rails, ties and ballast.
10.12 | Track: Special (switches, turnouts) | Include transitional curves.
10.13 | Track: Vibration and noise dampening | Include upcharge for vib/noise dampening to any track condition above.
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | As associated with stations, include costs for rough grading, excavation, station structures, enclosures, finishes, equipment; mechanical and electrical components including HVAC, ventilation shafts and equipment, station power, lighting, public address/customer information system, safety systems such as fire detection and prevention, security surveillance, access control, life safety systems, etc. Include all construction materials and labor regardless of whom is performing the work. NOTE: Count paired inbound/outbound boarding platforms as one station - do not report the total number of boarding platforms.
Put guideway and track associated with stations in 10 Guideway & Track Elements above.
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform | Include station structures including caissons, columns, platforms, superstructures, etc.
20.03 | Underground station, stop, shelter, mall, terminal, platform | Include retaining walls, backfill, structure.
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development | Per FTA's Joint Development Guidance, "Joint development is any income-producing activity with a transit nexus related to a real estate asset in which FTA has an interest. ...Joint development projects are commercial, residential, industrial, or mixed-use developments that are induced by or enhance the effectiveness of transit projects. . ."
20.06 | Automobile parking multi-story structure | Include retaining walls, backfill, structure.
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | As associated with support facilities, include costs for rough grading, excavation, support structures, enclosures, finishes, equipment; mechanical and electrical components including HVAC, ventilation shafts and equipment, facility power, lighting, public address system, safety systems such as fire detection and prevention, security surveillance, access control, life safety systems, etc. Include fueling stations. Include all construction materials and labor regardless of whom is performing the work.
Where a support facility shares the structure with a station, its cost may be included with station cost. Identify this with a note.
Except for guideway and track associated with a yard, include all guideway and track costs associated with support facilities in 10 Guideway & Track Elements above.
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility | Include service, inspection, and storage facilities and equipment.
30.03 | Heavy Maintenance Facility | Include heavy maintenance and overhaul facilities and equipment.
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track | Include yard construction, guideway and track associated with yard.
40 SITEWORK & SPECIAL CONDITIONS |  | Include all construction materials and labor regardless of whom is performing the work.
40.01 | Demolition, Clearing, Earthwork | Include project-wide clearing, demolition and fine grading.
40.02 | Site Utilities, Utility Relocation | Include all site utilities - storm, sewer, water, gas, electric.
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | Include underground storage tanks, fuel tanks, other hazardous materials and treatments, etc.
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | Include other environmental mitigation not listed.
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping | Include sidewalks, paths, plazas, functional landscaping, site and station furniture, site lighting, signage, bike facilities, permanent fencing.
40.07 | Automobile, bus, van accessways including roads, parking lots | Include all on-grade paving.
40.08 | Temporary Facilities and other indirect costs during construction | As a general rule and to the extent possible, appropriately allocate indirect costs among the construction costs in Categories 10 through 50. Where that is not possible, include in 40.08 Temporary Facilities costs for mobilization, demobilization, phasing; time and temporary construction associated with weather (heat, rain, freezing, etc.); temporary power and facilities; temporary construction, easements, and barriers for storm water pollution prevention, temporary access and to mitigate construction impacts; project and construction supervision; general conditions, overhead, profit. NOTE: Include contractor's general liability and other insurance related to construction such as builder's risk in Cats. 10 - 50, not in 80 Professional Services below.
50 SYSTEMS |  | Include all construction materials and labor regardless of whom is performing the work.
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection | Include signal prioritization at intersections.
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications | Include passenger information systems at stations and on vehicles (real time travel information; static maps and schedules). Include equipment to allow communications among vehicles and with central control.
50.06 | Fare collection system and equipment | Include fare sales and swipe machines, fare counting equipment.
50.07 | Central Control
Construction Subtotal (10 - 50)
60 ROW, LAND, EXISTING IMPROVEMENTS |  | Include professional services associated with the real estate component of the project. These costs may include agency staff oversight and administration, real estate and relocation consultants, legal counsel, court expenses, insurance, etc.
60.01 | Purchase or lease of real estate | If the value of right-of-way, land, and existing improvements is to be used as local match to the Federal funding of the project, include the total cost on this line item. In backup documentation, separate cost for land from cost for improvements. Identify whether items are leased, purchased or acquired through payment or for free. Include the costs for permanent surface and subsurface easements, trackage rights, etc.
60.02 | Relocation of existing households and businesses | In compliance with Uniform Relocation Act.
70 VEHICLES (number) |  | Include professional services associated with the vehicle component of the project. These costs may include agency staff oversight and administration, vehicle consultants, design and manufacturing contractors, legal counsel, warranty and insurance costs, etc.
70.01 | Light Rail | Include light rail and streetcar rail using electric, diesel or other power supply.
70.02 | Heavy Rail
70.03 | Commuter Rail | Include locomotives (diesel, electric, or other), trailer cars, self-propelled multiple units (EMU electric or DMU diesel, or other power supply)
70.04 | Bus | Includes "rubber-tired" buses and trolleys including new, used, historic replica, articulated, using electric, diesel, dual-power, or other power supply.
70.05 | Other | Include Vans, Sedan/Station Wagon, Cable Car, People Mover, Monorail, Car/Inclined Railway, Ferry Boat, Transferred Vehicle
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | Cat. 80 applies to Cats. 10-50. Cat. 80 includes all professional, technical and management services related to the design and construction of fixed infrastructure (Cats. 10 - 50) during the project development and construction phases of the project. This includes environmental work, design, engineering and architectural services; specialty services such as safety or security analyses; value engineering, risk assessment, cost estimating, scheduling, ridership modeling and analyses, auditing, legal services, administration and management, etc. by agency staff or outside consultants. Include professional liability insurance and other non-construction insurance on 80.05 unless insurance for the agency and its consultants is already included in other lines. Include costs associated with professional services related to real estate and vehicles in Cats. 60 and 70. (Note that costs for planning activities and NEPA work done before FTA approval to enter project development (PD), regardless of funding source, are not included in an SSGA and therefore, should not be included in the Standard Cost Category worksheets. For example, on one and the same grant, costs incurred prior to FTA approval to enter PD should be omitted from these worksheets whereas costs incurred after FTA approval to enter PD should be included.)
80.01 | Project Development
80.02 | Engineering (not applicable to Small Starts)
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Professional Liability and other Non-Construction Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up | Include start up and training. Include in Cats. 10 - 50 above access and protection work by agency staff or outside contractors.
Subtotal (10 - 80)
90 UNALLOCATED CONTINGENCY |  | Includes unallocated contingency, project reserves. Document allocated contingencies for individual line items on the BUILD Main worksheet.
Subtotal (10 - 90)
100 FINANCE CHARGES |  | Include finance charges expected to be paid by the project sponsor/grantee prior to either the completion of the project or the fulfillment of the Small Starts funding commitment, whichever occurs later in time. Finance charges incurred after this date should not be included in Total Project Cost. (See FFGA Circular FTA C5200.1A Chapter III for additional information.) Derive finance charges from the Small Starts project's financial plan, based on an analysis of the sources and uses of funds. The amount and type of debt financing required and revenues available determine the finance charges. By year, compute finance charges in year-of-expenditure (YOE) dollars. On the Inflation worksheet enter the finance charges for the appropriate years.
Total Project Cost (10 - 100)

## TrAMS Scopes ALIs
14-Series TrAMS Scope / Activity Line Items Required for all grants that serve a Capital Project
(Rev.21, June 2019)
1. HOW DO THE SCC AND TrAMS RELATE? TrAMS is for grants management. Many grants can serve a capital project -- e.g. CMAQ, 5307, 5309, etc. The Standard Cost Categories (SCC) are for cost management practice at important milestones. To manage capital project costs use the SCC worksheets, back up sheets, detailed cost estimates, etc. At important milestones, "paperclip" the SCC worksheets to the applicable grants in TrAMS. TrAMS and the SCC support each. 2. WHEN SHOULD I USE THE 14-SERIES? Use it for capital projects. For a New Starts project, use it from the very first grant that funds Project Development, and include all grants issued through the FFGA; these grants may be small or large and may derive funding from diverse sources such as CMAQ, 5307, 5309 Capital Investment Grants, Federal Non-Transportation funding from HUD, Defense, etc. 3. HOW IS THE 14-SERIES ORGANIZED AND WHY? The 14-Series has one Scope and 10 ALIs. The organization is intentionally simple. Put guideway costs under the Guideway ALI, station costs under the Station ALI. If the costs are organized simply, the information will be consistent program-wide and will produce a reliable database. For Vehicles, use the 13-Series ALIs. | 140-00 | PROJECT NAME - (this is the one Scope)
| 14.01.10 | GUIDEWAY & TRACK ELEMENTS |  | .01 Bus STD 40 FT
.02 Bus STD 35 FT
.03 Bus 30 FT
| 14.02.20 | STATIONS, STOPS, TERMINALS, INTERMODAL |  | .04 Bus < 30 FT
.05 Bus School
.06 Bus Articulated
| 14.03.30 | SUPPORT FACILITIES: YARDS, SHOPS, ADMIN BLDGS |  | .07 Bus Commuter / Suburban
.08 Bus Intercity
.09 Bus Trolley STD
| 14.04.40 | SITEWORK & SPECIAL CONDITIONS | Engineering & Design | .10 Bus Trolley Artic.
|  |  | 13.11.XX | .11 Bus Double Deck
.12 Bus Used
| 14.05.50 | SYSTEMS | Purchase - Replacement | .13 Bus School Used
|  |  | 13.12.XX | .14 Bus Dual Mode
.15 Vans
| 14.06.60 | ROW, LAND, EXISTING IMPROVEMENTS | Purchase - Expansion | .16 Sedan / Station Wagon
|  |  | 13.13.XX | .20 Light Rail Cars
.21 Heavy Rail Cars
| 13____ | VEHICLES - use the 13-Series ALIs for vehicles. | Rehabilitation / Rebuild | .22 Commuter Rail Self Propelled Electric
|  |  | 13.14.XX | .23 Commuter Rail Car Trailer
.24 Commuter Rail Locomotive Diesel
| 14.08.80 | PROFESSIONAL SERVICES | Mid Life Rebuild (Rail) | .25 Commuter Rail Locomotive Electric
|  |  | 13.15.XX | .26 Commuter Rail Cars Used
.27 Commuter Rail Locomotive Used
| 14.09.90 | UNALLOCATED CONTINGENCY | Lease - Replacement | .28 Commuter Rail Self Propelled - Diesel
|  |  | 13.16.XX | .30 Cable Car
.31 People Mover
| 14.10.10 | FINANCE CHARGES | Lease - Expansion | .32 Car, Incline Railway
|  |  | 13.18.XX | .33 Ferry Boats
.39 Transferred Vehicles
|  |  | Vehicle Overhaul | .40 Spare Parts/Assoc.Capital
|  |  | 13.17.00 | / Maintenance Items

## Build Main
M A I N W O R K S H E E T - B U I L D A L T E R N A T I V E | [8 empty] | (Rev.21, June 2019)
Port Authority Allegheny County / City of Pittsburgh | [6 empty] | Today's Date |  | 2019-10-02 13:08
Pittsburgh BRT | [6 empty] | Yr of Base Year $ |  | 2019
Engineering - 60% VE Estimate | [6 empty] | Yr of Revenue Ops |  | 2024
|  | Quantity | Base Year Dollars w/o Contingency (X000) | Base Year Dollars Allocated Contingency (X000) | Base Year Dollars TOTAL (X000) | Base Year Dollars Unit Cost (X000) | Base Year Dollars Percentage of Construction Cost | Base Year Dollars Percentage of Total Project Cost | YOE Dollars Total (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 14.95 | 29226452.64 | 3117231.9 | 32343684.54 | 2163457.1599 | 24.61% | 14.55% | 36341075.2531 | 1.1236
10.01 | Guideway: At-grade exclusive right-of-way |  | 0 | 0 | 0 |  |  |  | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 14.95 | 29226452.64 | 3117231.9 | 32343684.54 | 2163457.1599 |  |  | 36341075.2531
10.03 | Guideway: At-grade in mixed traffic |  | 0 | 0 | 0 |  |  |  | 0
10.04 | Guideway: Aerial structure |  | 0 | 0 | 0 |  |  |  | 0
10.05 | Guideway: Built-up fill |  | 0 | 0 | 0 |  |  |  | 0
10.06 | Guideway: Underground cut & cover |  | 0 | 0 | 0 |  |  |  | 0
10.07 | Guideway: Underground tunnel |  | 0 | 0 | 0 |  |  |  | 0
10.08 | Guideway: Retained cut or fill |  | 0 | 0 | 0 |  |  |  | 0
10.09 | Track: Direct fixation |  | 0 | 0 | 0 |  |  |  | 0
10.1 | Track: Embedded |  | 0 | 0 | 0 |  |  |  | 0
10.11 | Track: Ballasted |  | 0 | 0 | 0 |  |  |  | 0
10.12 | Track: Special (switches, turnouts) |  | 0 | 0 | 0 |  |  |  | 0
10.13 | Track: Vibration and noise dampening |  | 0 | 0 | 0 |  |  |  | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 46 | 13385987.01 | 1380036.23 | 14766023.24 | 321000.5052 | 11.23% | 6.645% | 16645468.6597 | 1.1273
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 46 | 13385987.01 | 1380036.23 | 14766023.24 | 321000.5052 |  |  | 16645468.6597
20.02 | Aerial station, stop, shelter, mall, terminal, platform |  | 0 | 0 | 0 |  |  |  | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform |  | 0 | 0 | 0 |  |  |  | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. |  | 0 | 0 | 0 |  |  |  | 0
20.05 | Joint development |  | 0 | 0 | 0 |  |  |  | 0
20.06 | Automobile parking multi-story structure |  | 0 | 0 | 0 |  |  |  | 0
20.07 | Elevators, escalators |  | 0 | 0 | 0 |  |  |  | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 14.95 | 8134642.34 | 1188130.59 | 9322772.93 | 623596.8515 | 7.093% | 4.195% | 10820574.0263 | 1.1607
30.01 | Administration Building: Office, sales, storage, revenue counting |  | 0 | 0 | 0 |  |  |  | 0
30.02 | Light Maintenance Facility | 1 | 8134642.34 | 1188130.59 | 9322772.93 | 9322772.93 |  |  | 10820574.0263
30.03 | Heavy Maintenance Facility |  | 0 | 0 | 0 |  |  |  | 0
30.04 | Storage or Maintenance of Way Building |  | 0 | 0 | 0 |  |  |  | 0
30.05 | Yard and Yard Track |  | 0 | 0 | 0 |  |  |  | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 14.95 | 50306479.43 | 3919572.48 | 54226051.91 | 3627160.6629 | 41.26% | 24.4% | 60969971.2519 | 1.1244
40.01 | Demolition, Clearing, Earthwork | 14.95 | 262818.68 | 20825.23 | 283643.91 | 18972.8368 |  |  | 318919.7891
40.02 | Site Utilities, Utility Relocation | 14.95 | 17965107.16 | 1170751.83 | 19135858.99 | 1279990.5679 |  |  | 21515724.1106
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 14.95 | 83901.21 | 0 | 83901.21 | 5612.1211 |  |  | 94335.7331
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 0 | 0 | 0 |  |  |  | 0
40.05 | Site structures including retaining walls, sound walls |  | 0 | 0 | 0 |  |  |  | 0
40.06 | Pedestrian / bike access and accommodation, landscaping | 14.95 | 5912532.46 | 591253.25 | 6503785.71 | 435035.8334 |  |  | 7312640.5814
40.07 | Automobile, bus, van accessways including roads, parking lots |  | 0 | 0 | 0 |  |  |  | 0
40.08 | Temporary Facilities and other indirect costs during construction | 14.95 | 26082119.92 | 2136742.17 | 28218862.09 | 1887549.3037 |  |  | 31728351.0377
50 SYSTEMS |  | 14.95 | 18883333.9 | 1888333.39 | 20771667.29 | 1389409.1833 | 15.8% | 9.347% | 23662189.5767 | 1.1392
50.01 | Train control and signals |  | 0 | 0 | 0 |  |  |  | 0
50.02 | Traffic signals and crossing protection | 14.95 | 12182669.17 | 1218266.91 | 13400936.08 | 896383.6843 |  |  | 15265769.7431
50.03 | Traction power supply: substations |  | 0 | 0 | 0 |  |  |  | 0
50.04 | Traction power distribution: catenary and third rail |  | 0 | 0 | 0 |  |  |  | 0
50.05 | Communications | 14.95 | 2037505.36 | 203750.54 | 2241255.9 | 149916.7826 |  |  | 2553142.2806
50.06 | Fare collection system and equipment | 14.95 | 4468616.48 | 446861.65 | 4915478.13 | 328794.5237 |  |  | 5599501.1738
50.07 | Central Control | 14.95 | 194542.89 | 19454.29 | 213997.18 | 14314.1926 |  |  | 243776.3792
Construction Subtotal (10 - 50) |  | 14.95 | 119936895.32 | 11493304.59 | 131430199.91 | 8791317.7197 | 100% | 59.14% | 148439278.7678
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 14.95 | 5597955.84 | 2239182.34 | 7837138.18 | 524223.2896 |  | 3.527% | 8317315.3259 | 1.0613
60.01 | Purchase or lease of real estate | 1 | 5597955.84 | 2239182.34 | 7837138.18 | 7837138.18 |  |  | 8317315.3259
60.02 | Relocation of existing households and businesses |  | 0 | 0 | 0 |  |  |  | 0
70 VEHICLES (number) |  | 67 | 24821818.1 | 361468.18 | 25183286.28 | 375869.9445 |  | 11.33% | 28933559.1132 | 1.1489
70.01 | Light Rail |  | 0 | 0 | 0 |  |  |  | 0
70.02 | Heavy Rail |  | 0 | 0 | 0 |  |  |  | 0
70.03 | Commuter Rail |  | 0 | 0 | 0 |  |  |  | 0
70.04 | Bus | 66 | 24671818.1 | 361468.18 | 25033286.28 | 379292.2164 |  |  | 28761221.2452
70.05 | Other | 1 | 150000 | 0 | 150000 | 150000 |  |  | 172337.868
70.06 | Non-revenue vehicles |  | 0 | 0 | 0 |  |  |  | 0
70.07 | Spare parts |  | 0 | 0 | 0 |  |  |  | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | 14.95 | 39842538.13 | 0 | 39842538.13 | 2665052.7177 | 30.31% | 17.93% | 42496643.2991 | 1.0666
80.01 | Project Development |  | 24065066.28 |  | 24065066.28 |  |  |  | 25668157.3431
80.02 | Engineering (not applicable to Small Starts) |  | 0
80.03 | Project Management for Design and Construction |  | 2628604 |  | 2628604 |  |  |  | 2803708.092
80.04 | Construction Administration & Management |  | 10520263.85 |  | 10520263.85 |  |  |  | 11221069.7719
80.05 | Professional Liability and other Non-Construction Insurance |  | 657151 |  | 657151 |  |  |  | 700927.023
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 657151 |  | 657151 |  |  |  | 700927.023
80.07 | Surveys, Testing, Investigation, Inspection |  | 657151 |  | 657151 |  |  |  | 700927.023
80.08 | Start up |  | 657151 |  | 657151 |  |  |  | 700927.023
Subtotal (10 - 80) |  | 14.95 | 190199207.39 | 14093955.11 | 204293162.5 | 13665094.4816 |  | 91.93% | 228186796.5059
90 UNALLOCATED CONTINGENCY |  |  |  |  | 17925987.62 |  |  | 8.067% | 21717799.3136 | 1.2115
Subtotal (10 - 90) |  | 14.95 |  |  | 222219150.12 | 14864157.1987 |  | 100% | 249904595.8195
100 FINANCE CHARGES |  |  |  |  | 0 |  |  | 0% | 0 | #DIV/0!
Total Project Cost (10 - 100) |  | 14.95 |  |  | 222219150.12 | 14864157.1987 |  | 100% | 249904595.8195 | 1.1246
Allocated Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 7.41%
Unallocated Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 9.425%
Total Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 16.83%
Unallocated Contingency as % of Subtotal (10 - 80) |  |  |  |  | 8.775%
YOE Construction Cost per Mile (X000) | [8 empty] | 9929048.747
YOE Total Project Cost per Mile Not Including Vehicles (X000) | [8 empty] | 14780671.3516
YOE Total Project Cost per Mile (X000) | [8 empty] | 16716026.4762
Note on J3: Year of Base Year Dollars should match the year in "Today's Date."
Note on J6: YOE Dollars automatically arrive from Inflation Worksheet.
Note on D8: For all cells, enter costs to the nearest $1. Note, all costs will be displayed to the nearest $1,000! 'Green' shaded areas are computed automatically and locked by FTA. 'White' cells should be used for manual entry.
Note on J8: YOE costs for individual line items within a Category are derived as a percentage of the YOE cost of the Category.
Note on I19: Preparing for bid: For each separate contract package generate a Main Worksheet and an Inflation Worksheet separately, and aggregate into this Build Main worksheet. Additional worksheets should be maintained for contract billing and reporting only. DO NOT alter the SCC workbook to create/insert additional worksheets. In the Special Conditions of the Contract, require the construction contractor to update these worksheets and submit them with the monthly pay application. This should make it easy to track costs in the SCC format throughout construction, and make it easy to submit the final costs to FTA at contract closeout.
Note on F76: Enter finance charges on Inflation Worksheet.

## Inflation
I N F L A T I O N W O R K S H E E T |  |  |  |  | (Rev.21, June 2019)
Port Authority Allegheny County / City of Pittsburgh |  |  | Today's Date |  | 2019-10-02 13:08
Pittsburgh BRT |  |  | Yr of Base Year $ |  | 2019
Engineering - 60% VE Estimate |  |  | Yr of Revenue Ops |  | 2024
Insert comments, notes, etc.
BASE YEAR DOLLARS (X$000) | Base Yr Dollars | Double-Check Total | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 32343684.54 | 32343684.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12937473.816 | 12937473.816 | 6468736.908 | 0 | [11 empty] | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 14766023.24 | 14766023.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2953204.648 | 10336216.268 | 1476602.324 | 0 | [11 empty] | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 9322772.93 | 9322772.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2330693.2325 | 6992079.6975 | 0 | [11 empty] | 0
40 SITEWORK & SPECIAL CONDITIONS | 54226051.91 | 54226051.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5422605.191 | 16267815.573 | 16267815.573 | 16267815.573 | 0 | [11 empty] | 0
50 SYSTEMS | 20771667.29 | 20771667.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4154333.458 | 8308666.916 | 8308666.916 | 0 | [11 empty] | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 7837138.18 | 7837138.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391856.909 | 1959284.545 | 2742998.363 | 2742998.363 | 0 | 0 | 0 | [11 empty] | 0
70 VEHICLES (number) | 25183286.28 | 25183286.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2518328.628 | 8814150.198 | 13850807.454 | 0 | [11 empty] | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 39842538.13 | 39842538.1349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1425862.0231 | 2396737.9618 | 7103838.9 | 5783219.85 | 5783219.85 | 5783219.85 | 5783219.85 | 5783219.85 | 0 | [11 empty] | 0
90 UNALLOCATED CONTINGENCY | 17925987.62 | 17925987.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17925987.62 | [11 empty] | 0
100 FINANCE CHARGES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 222219150.12 | 222219150.1249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1425862.0231 | 2396737.9618 | 7495695.809 | 7742504.395 | 13948823.404 | 47357374.336 | 64778235.8535 | 59147928.7225 | 17925987.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inflation Rate |  |  | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035
Compounded Inflation Factor |  |  | 1.4965 | 1.4459 | 1.397 | 1.3498 | 1.3041 | 1.26 | 1.2174 | 1.1762 | 1.1365 | 1.098 | 1.0609 | 1.03 | 1 | 1.03 | 1.0609 | 1.0927 | 1.131 | 1.1706 | 1.2115 | 1.2539 | 1.2978 | 1.3432 | 1.3903 | 1.4389 | 1.4893 | 1.5414 | 1.5953 | 1.6512 | 1.709 | 1.7688 | 1.8307
YEAR OF EXPENDITURE DOLLARS (X$000) | YOE Dollars |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 36341075.2531 | [13 empty] | 0 | 0 | 0 | 14137126.9505 | 14631926.3938 | 7572021.9088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 16645468.6597 | [13 empty] | 0 | 0 | 0 | 3227046.4554 | 11689975.7847 | 1728446.4196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10820574.0263 | [13 empty] | 0 | 0 | 0 | 0 | 2635949.8237 | 8184624.2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 60969971.2519 | [13 empty] | 0 | 0 | 5752841.8471 | 17776281.3076 | 18398451.1534 | 19042396.9438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS | 23662189.5767 | [13 empty] | 0 | 0 | 0 | 4539552.3366 | 9396873.3367 | 9725763.9035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 8317315.3259 | [13 empty] | 391856.909 | 2018063.0813 | 2910046.9633 | 2997348.3722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number) | 28933559.1132 | [13 empty] | 0 | 0 | 0 | 2751845.6867 | 9968561 | 16213152.4265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 42496643.2991 | [11 empty] | 1344011.71 | 2326930.06 | 7103838.9 | 5956716.4455 | 6135417.9389 | 6319480.477 | 6540662.2937 | 6769585.474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 21717799.3136 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 21717799.3136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 FINANCE CHARGES | 0
Total Project Cost (10 - 100) | 249904595.8195 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344011.71 | 2326930.06 | 7495695.809 | 7974779.5268 | 14798306.7493 | 51748681.5861 | 73262399.786 | 69235991.2787 | 21717799.3136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on Q21: In the Base Year no inflation multiplier is used.
Note on E24: For past years, enter the actual dollars spent in each year. The dollars will inflate when converted to the current base year.
Note on E33: Enter Finance Charges on this line.

## Project Description
P R O J E C T D E S C R I P T I O N - B U I L D A L T E R N A T I V E |  |  |  | (Rev.21, June 2019)
Port Authority Allegheny County / City of Pittsburgh |  |  | Today's Date | 2019-10-02 13:08
Pittsburgh BRT
Engineering - 60% VE Estimate
Describe the project elements to explain the unit costs shown on the Main Worksheet. Example: A 20-mile new light rail project has its guideway entirely on grade except for a one-eighth mile bridge over a river. The bridge or aerial structure may have a relatively high unit cost because there is little economy of scale. Mention precedents and reference points used in the development of costs for this project. Mention other aspects of this project that were important considerations in estimating costs. These could include the physical context, site constraints; design parameters; institutional, contracting and procurement conditions; project schedule, etc.
10 GUIDEWAY & TRACK ELEMENTS (route miles)
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | Includes costs associated with construction of the BRT alignment, including demolition and clearing, excavations, roadway pavement and bases, sidewalks, curbs, signage, lighting, pavement markings, plantings, etc.
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
20.01 | At-grade station, stop, shelter, mall, terminal, platform | Includes all costs associated with bus shelter procurement, bus shelter installation, comfort stations and all associated infrastructure, and furnishings.
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
30.02 | Light Maintenance Facility | Includes costs assocuated with Plug in and On-Route Charging systems for electric buses.
40 SITEWORK & SPECIAL CONDITIONS
40.02 | Site Utilities, Utility Relocation | Includes costs associated with new or relocated utilities, including an anticipated portion of the estimated total cost of utility replacement along forbes and fifth in the uptown neighborhood to be performed by others.
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | Includes costs associated with unforeen water pollution control.
40.06 | Pedestrian / bike access and accommodation, landscaping | Includes costs associated with landscaping, sidewalks, bike lane marking.
40.08 | Temporary Facilities and other indirect costs during construction | Includes costs associated with maintenance and protection of traffic, contractor general conditions, quality control management, construction monitoring, and sales tax.
50 SYSTEMS
50.02 | Traffic signals and crossing protection | Includes costs associated with traffic signals including signal assemblies, software and programming, cabinets, signal supports, signal heads, radar detection, fiber optics, smart spine, priority equipment and all related commissioning.
50.05 | Communications | Includes costs assosciated with various systems including automatic vehicle location systems at stations, CCTV cameras, wireless networking equipment, security stations/call buttons & all related infrastructure & commissioning.
50.06 | Fare collection system and equipment | Includes ticket vending machines and associated shelters.
50.07 | Central Control | Includes costs associated with Genetec video management systems, wireless basestation units and related headend work.
Construction Subtotal (10 - 50)
60 ROW, LAND, EXISTING IMPROVEMENTS
60.01 | Purchase or lease of real estate | Includes costs associated with right of way acquisition along the BRT alignment.
70 VEHICLES (number)
70.04 | Bus | Includes coasts associated with procurement of battery electric buses, additional 60' diesel articulated buses and all associated special tools, spare parts and rebranding of existing buses with BRT graphics.
70.05 | Other | Includes the cost of an art allowance.
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
80.01 | Project Development | This cost will include preliminary engineering up to final design including design services during construction.
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management | An estimated Professional Services percentage is included for PAAC/City of Pittsburgh PM staff for administration and force account work, as well as City of Pittsburgh inspectors and project manager.
80.05 | Professional Liability and other Non-Construction Insurance | Project insurance includes all premium costs to provide “wrap-up” insurance coverage through a Contractor Controlled Insurance Program (CCIP). This category will include professional liability, comprehensive general liability, builder’s risk, worker’s compensation and employer’s liability, construction equipment loss or damage, and automobile insurance.
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | Includes legal fees (except real estate legal fees), permitting fees, and review fees by other entities.
80.07 | Surveys, Testing, Investigation, Inspection | This item includes independent testing, third party surveying during construction to confirm progressed work, investigations of contractor claims or differing site conditions, and special inspections required by PAAC/City of Pittsburgh, or the local building authorities.
80.08 | Start up | This sub-category will include the costs in training transit personnel and testing of the new systems. This includes safety certification and activation.
Subtotal (10 - 80)
90 UNALLOCATED CONTINGENCY |  | Includes unallocated contingency, project reserves.
Subtotal (10 - 90)
100 FINANCE CHARGES
Total Project Cost (10 - 100)

## Schedule
S C H E D U L E |  |  | (Rev.21, June 2019)
Port Authority Allegheny County / City of Pittsburgh | Today's Date |  | 2019-10-02 13:08
Pittsburgh BRT | Yr of Base Year $ |  | 2019
Engineering - 60% VE Estimate | Yr of Revenue Ops |  | 2024
Insert comments, notes, etc. |  | Start Date | End Date | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 2021-03-30 | 2024-07-26
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 2021-03-30 | 2024-07-26
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 2021-03-30 | 2024-07-26
40 SITEWORK & SPECIAL CONDITIONS |  | 2021-03-30 | 2024-07-26
50 SYSTEMS |  | 2021-03-30 | 2024-07-26
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 2019-10-01 | 2022-08-31
70 VEHICLES (number) |  | 2022-03-21 | 2023-07-21
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | 2017-06-01 | 2025-05-30
90 UNALLOCATED CONTINGENCY |  | 2024-09-06 | 2025-05-30
100 FINANCE CHARGES (CC Only)
REVENUE OPERATIONS |  | 2024-09-06
Note on E6: Delete years that are not applicable.

## Build Annualized
A N N U A L I Z E D C O S T - B U I L D A L T E R N A T I V E (Current Year) | [9 empty] | (Rev.21, June 2019)
Port Authority Allegheny County / City of Pittsburgh | [7 empty] | Today's Date |  | 2019-10-02 13:08
Pittsburgh BRT | [7 empty] | Yr of Base Year $ |  | 2019
Engineering - 60% VE Estimate | [7 empty] | Yr of Revenue Ops |  | 2024
|  | Quantity | Total Base Year Dollars (X000) | Cat. 80 Prof. Svc. spread proportionally over Cats. 10 - 50 (X000) | Spread Cat. 90 Unalloc. Cont. according to perceived risks (X000) | Revised Total Base Year Dollars (X000) | Federal Share of Base Year Dollars (based on 64.8 percent Federal funding share) | Years of Useful Life | Annualization Factor (based on 2% rate) [.02/1 - (1.02)^-no. yrs] | Annualized Federal Share (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 14.95 | 32343684.54 | 9804858.2855 | 3698382.4992 | 45846925.3247 | 29704694.8387 |  |  | 1326312.3163
10.01 | Guideway: At-grade exclusive right-of-way | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0.021837 | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 14.95 | 32343684.54 | 9804858.2855 | 3698382.4992 | 45846925.3247 | 29704694.8387 | 30 | 0.04465 | 1326312.3163
10.03 | Guideway: At-grade in mixed traffic | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.061157 | 0
10.04 | Guideway: Aerial structure | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0.025161 | 0
10.05 | Guideway: Built-up fill | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0.025161 | 0
10.06 | Guideway: Underground cut & cover | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0.021837 | 0
10.07 | Guideway: Underground tunnel | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0.021837 | 0
10.08 | Guideway: Retained cut or fill | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0.021837 | 0
10.09 | Track: Direct fixation |  | 0 | 0 | 0 | 0 | 0 | 30 | 0.04465 | 0
10.1 | Track: Embedded |  | 0 | 0 | 0 | 0 | 0 | 20 | 0.061157 | 0
10.11 | Track: Ballasted |  | 0 | 0 | 0 | 0 | 0 | 35 | 0.040002 | 0
10.12 | Track: Special (switches, turnouts) |  | 0 | 0 | 0 | 0 | 0 | 30 | 0.04465 | 0
10.13 | Track: Vibration and noise dampening |  | 0 | 0 | 0 | 0 | 0 | 30 | 0.04465 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 46 | 14766023.24 | 4476260.7405 | 1688440.9649 | 20930724.9454 | 13561232.1405 |  |  | 361646.1725
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 46 | 14766023.24 | 4476260.7405 | 1688440.9649 | 20930724.9454 | 13561232.1405 | 70 | 0.026668 | 361646.1725
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0.026668 | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0.021837 | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0.026668 | 0
20.05 | Joint development |  | 0 | 0 | 0 | 0 | 0 | 70 | 0.026668 | 0
20.06 | Automobile parking multi-story structure |  | 0 | 0 | 0 | 0 | 0 | 50 | 0.031823 | 0
20.07 | Elevators, escalators |  | 0 | 0 | 0 | 0 | 0 | 30 | 0.04465 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  |  | 9322772.93 | 2826161.2338 | 1066025.1217 | 13214959.2855 | 8562108.148 |  |  | 272473.7631
30.01 | Administration Building: Office, sales, storage, revenue counting |  | 0 | 0 | 0 | 0 | 0 | 50 | 0.031823 | 0
30.02 | Light Maintenance Facility |  | 9322772.93 | 2826161.2338 | 1066025.1217 | 13214959.2855 | 8562108.148 | 50 | 0.031823 | 272473.7631
30.03 | Heavy Maintenance Facility |  | 0 | 0 | 0 | 0 | 0 | 50 | 0.031823 | 0
30.04 | Storage or Maintenance of Way Building |  | 0 | 0 | 0 | 0 | 0 | 50 | 0.031823 | 0
30.05 | Yard and Yard Track |  | 0 | 0 | 0 | 0 | 0 | 80 | 0.025161 | 0
40 SITEWORK & SPECIAL CONDITIONS |  |  | 54226051.91 | 16438410.2158 | 6200551.4905 | 76865013.6163 | 49801633.5245 |  |  | 1357780.3317
40.01 | Demolition, Clearing, Earthwork |  | 283643.91 | 85985.514 | 32433.6478 | 402063.0718 | 260500.8028 | 125 | 0.021837 | 5688.631
40.02 | Site Utilities, Utility Relocation |  | 19135858.99 | 5800958.9271 | 2188115.7636 | 27124933.6807 | 17574523.7396 | 125 | 0.021837 | 383779.9358
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  | 83901.21 | 25434.3154 | 9593.7977 | 118929.3231 | 77055.5326 | 125 | 0.021837 | 1682.6839
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 0 | 0 | 0 | 0 | 0 | 125 | 0.021837 | 0
40.05 | Site structures including retaining walls, sound walls |  | 0 | 0 | 0 | 0 | 0 | 80 | 0.025161 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 6503785.71 | 1971596.5609 | 743684.2027 | 9219066.4736 | 5973128.0638 | 20 | 0.061157 | 365296.9093
40.07 | Automobile, bus, van accessways including roads, parking lots |  | 0 | 0 | 0 | 0 | 0 | 20 | 0.061157 | 0
40.08 | Temporary Facilities and other indirect costs during construction |  | 28218862.09 | 8554434.8983 | 3226724.0787 | 40000021.0671 | 25916425.3857 | 100 | 0.023203 | 601332.1716
50 SYSTEMS |  |  | 20771667.29 | 6296847.6544 | 2375164.4835 | 29443679.4279 | 19076862.977 |  |  | 915419.854
50.01 | Train control and signals |  | 0 | 0 | 0 | 0 | 0 | 30 | 0.04465 | 0
50.02 | Traffic signals and crossing protection |  | 13400936.08 | 4062440.0413 | 1532348.2212 | 18995724.3424 | 12307525.3321 | 30 | 0.04465 | 549530.0497
50.03 | Traction power supply: substations |  | 0 | 0 | 0 | 0 | 0 | 50 | 0.031823 | 0
50.04 | Traction power distribution: catenary and third rail |  | 0 | 0 | 0 | 0 | 0 | 30 | 0.04465 | 0
50.05 | Communications |  | 2241255.9 | 679427.7397 | 256279.4473 | 3176963.087 | 2058387.0858 | 20 | 0.061157 | 125884.1988
50.06 | Fare collection system and equipment |  | 4915478.13 | 1490107.4864 | 562067.0171 | 6967652.6335 | 4514413.8621 | 25 | 0.05122 | 231230.2572
50.07 | Central Control |  | 213997.18 | 64872.3871 | 24469.7979 | 303339.365 | 196536.697 | 30 | 0.04465 | 8775.3482
Construction Subtotal (10 - 50) |  |  | 131430199.91 | 39842538.13 | 15028564.5598 | 186301302.5998 | 120706531.6286 |  |  | 4233632.4375
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | 7837138.18 |  | 687680.5874 | 8524818.7674 | 5523317.8288 |  |  | 120614.282
60.01 | Purchase or lease of real estate |  | 7837138.18 |  | 687680.5874 | 8524818.7674 | 5523317.8288 | 125 | 0.021837 | 120614.282
60.02 | Relocation of existing households and businesses |  | 0 |  | 0 | 0 | 0 | 125 | 0.021837 | 0
70 VEHICLES (number) |  | 67 | 25183286.28 |  | 2209742.4728 | 27393028.7528 | 17748225.2964 |  |  | 1678265.0248
70.01 | Light Rail | 0 | 0 |  | 0 | 0 | 0 | 25 | 0.05122 | 0
70.02 | Heavy Rail | 0 | 0 |  | 0 | 0 | 0 | 25 | 0.05122 | 0
70.03 | Commuter Rail | 0 | 0 |  | 0 | 0 | 0 | 25 | 0.05122 | 0
70.04 | Bus | 66 | 25033286.28 |  | 2196580.5143 | 27229866.7943 | 17642510.984 | 12 | 0.09456 | 1668268.7221
70.05 | Other | 1 | 150000 |  | 13161.9586 | 163161.9586 | 105714.3125 | 12 | 0.09456 | 9996.3027
70.06 | Non-revenue vehicles | 0 | 0 |  | 0 | 0 | 0 | 12 | 0.09456 | 0
70.07 | Spare parts | 0 | 0 |  | 0 | 0 | 0 | 12 | 0.09456 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  |  | 39842538.13
80.01 | Project Development |  | 24065066.28
80.02 | Engineering (not applicable to Small Starts) |  | 0
80.03 | Project Management for Design and Construction |  | 2628604
80.04 | Construction Administration & Management |  | 10520263.85
80.05 | Professional Liability and other Non-Construction Insurance |  | 657151
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 657151
80.07 | Surveys, Testing, Investigation, Inspection |  | 657151
80.08 | Start up |  | 657151
Subtotal (10 - 80) |  |  | 204293162.5
90 UNALLOCATED CONTINGENCY |  |  | 17925987.62
TOTAL |  |  | 222219150.12 | 39842538.13 | 17925987.62 | 222219150.12 | 143978074.7539 |  |  | 6032511.7443
Note on I60: The range for buses is 12 to 18 years. Provide supporting documentation for an estimated useful life of more than 12 years.
Note on E75: E75 and F75 are double-checks

## Fund Source by Cat
F U N D I N G S O U R C E S B Y C A T E G O R Y | [11 empty] | (Rev.21, June 2019)
Port Authority Allegheny County / City of Pittsburgh | [9 empty] | Today's Date |  | 2019-10-02 13:08
Pittsburgh BRT
Engineering - 60% VE Estimate
| Cost |  | Funding Summary |  |  | Federal Sources |  |  |  |  | Local Sources
| YOE Cost (X000) | Double- check Total | Federal 5309 Small Starts Funds | Federal Other Funds | Local Funds | Federal 5309 Small Starts | CMAQ | SPC TIP | Spine | Other | PAAC | City of Pittsburgh |  |  |  | Allegheny County
[13 empty] | Pennsylvania | URA TRID | Project sponsor
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 36341075.2531 | 36341075.2531 | 7433789.2329 | 20000000 | 8907286.0203 | 7433789.2329 |  | 20000000 |  |  | 2907286.0203 | 2000000 |  | 1000000 | 1000000 | 2000000
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 16645468.6597 | 16645468.6597 | 7813831.1669 | 0 | 8831637.4928 | 7813831.1669 |  |  |  |  | 1331637.4928 | 1500000 | 2000000 | 1000000 | 1000000 | 2000000
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10820574.0263 | 10820574.0263 | 5954928.1042 | 0 | 4865645.9221 | 5954928.1042 |  |  |  |  | 865645.9221 |  |  | 1000000 | 1000000 | 2000000
40 SITEWORK & SPECIAL CONDITIONS | 60969971.2519 | 60969971.2519 | 10892373.5518 | 34400000 | 15677597.7002 | 10892373.5518 | 3200000 | 31200000 |  |  | 4877597.7002 | 6800000 |  | 1000000 | 1000000 | 2000000
50 SYSTEMS | 23662189.5767 | 23662189.5767 | 4085390.5906 | 7565760 | 12011038.9861 | 4085390.5906 | 1565760 |  | 6000000 |  | 2284415.1661 | 6000000 |  | 1000000 | 726623.82 | 2000000
60 ROW, LAND, EXISTING IMPROVEMENTS | 8317315.3259 | 8317315.3259 | 1651930.0998 | 0 | 6665385.2261 | 1651930.0998 |  |  |  |  | 665385.2261 | 4000000 |  |  |  | 2000000
70 VEHICLES (number) | 28933559.1132 | 28933559.1132 | 21146847.2906 | 0 | 7786711.8226 | 21146847.2906 |  |  |  |  | 5786711.8226 |  |  |  |  | 2000000
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 42496643.2991 | 42496643.2991 | 21326139.8352 | 0 | 21170503.4639 | 21326139.8352 |  |  |  |  | 3399731.4639 |  | 1212258 |  |  | 16558514
90 UNALLOCATED CONTINGENCY | 21717799.3136 | 21717799.3141 | 19644770.1281 | 0 | 2073029.1859 | 19644770.1281 |  |  |  |  | 1073029.1859 |  |  |  |  | 1000000
100 FINANCE CHARGES | 0 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 249904595.8195 | 249904595.82 | 99950000 | 61965760 | 87988835.82 | 99950000 | 4765760 | 51200000 | 6000000 | 0 | 23191440 | 20300000 | 3212258 | 5000000 | 4726623.82 | 31558514
Percentage of Total Project Cost | 100% |  | 40% | 24.8% | 35.21% | 40% | 1.907% | 20.49% | 2.401% | 0% | 9.28% | 8.123% | 1.285% | 2.001% | 1.891% | 12.63%
|  |  | 40% | 60%
100%
Note on R7: Insert additional columns as required.
Note on A9: Delete rows that are not needed.

## Fund Source by Year
F U N D I N G S O U R C E S B Y Y E A R |  |  |  |  | (Rev.21, June 2019)
Port Authority Allegheny County / City of Pittsburgh |  |  | Today's Date |  | 2019-10-02 13:08
Pittsburgh BRT
Engineering - 60% VE Estimate
| Total, All Years |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036
Total Project Cost In YOE Dollars Below insert funding sources and amounts for each year. | 249904595.8195 | double check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344011.71 | 2326930.06 | 7495695.809 | 7974779.5268 | 14798306.7493 | 51748681.5861 | 73262399.786 | 69235991.2787 | 21717799.3136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Federal 5309 Small Starts | 99950000 | 99950000 | 2021: 5000000; 2022: 25101743.2906; 2023: 25101743.2906; 2024: 25101743.2906; 2025: 19644770.1281
Local | 87988835.82 | 87988835.82 | 2017: 1344011.71; 2018: 2326930.06; 2019: 7495695.809; 2020: 7974779.5268; 2021: 4798306.7493; 2022: 7658351.6288; 2023: 29172069.8287; 2024: 25145661.3214; 2025: 2073029.1859
Federal Other | 61965760 | 61965760 | 2021: 5000000; 2022: 18988586.6667; 2023: 18988586.6667; 2024: 18988586.6667
Total Project Cost (10 - 100) | 249904595.82 | 249904595.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344011.71 | 2326930.06 | 7495695.809 | 7974779.5268 | 14798306.7493 | 51748681.5861 | 73262399.786 | 69235991.2787 | 21717799.3141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on N6: The information reported below should match what is reported in the financial plan. FTA uses this data to get an understanding of future demand for Section 5309 funds. The inputs should not assume Section 5309 funding in fiscal years for which appropriations have already occurred and the project did not receive anything.

## SSGA A3T1
Table 1 - BCE by Standard Cost Category
Applicable Line Items Only |  | YOE Dollars Total (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 36341075.2531
10.01 | Guideway: At-grade exclusive right-of-way | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 36341075.2531
10.03 | Guideway: At-grade in mixed traffic | 0
10.04 | Guideway: Aerial structure | 0
10.05 | Guideway: Built-up fill | 0
10.06 | Guideway: Underground cut & cover | 0
10.07 | Guideway: Underground tunnel | 0
10.08 | Guideway: Retained cut or fill | 0
10.09 | Track: Direct fixation | 0
10.1 | Track: Embedded | 0
10.11 | Track: Ballasted | 0
10.12 | Track: Special (switches, turnouts) | 0
10.13 | Track: Vibration and noise dampening | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 16645468.6597
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 16645468.6597
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0
20.05 | Joint development | 0
20.06 | Automobile parking multi-story structure | 0
20.07 | Elevators, escalators | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 10820574.0263
30.01 | Administration Building: Office, sales, storage, revenue counting | 0
30.02 | Light Maintenance Facility | 10820574.0263
30.03 | Heavy Maintenance Facility | 0
30.04 | Storage or Maintenance of Way Building | 0
30.05 | Yard and Yard Track | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 60969971.2519
40.01 | Demolition, Clearing, Earthwork | 318919.7891
40.02 | Site Utilities, Utility Relocation | 21515724.1106
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 94335.7331
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 0
40.05 | Site structures including retaining walls, sound walls | 0
40.06 | Pedestrian / bike access and accommodation, landscaping | 7312640.5814
40.07 | Automobile, bus, van accessways including roads, parking lots | 0
40.08 | Temporary Facilities and other indirect costs during construction | 31728351.0377
50 SYSTEMS |  | 23662189.5767
50.01 | Train control and signals | 0
50.02 | Traffic signals and crossing protection | 15265769.7431
50.03 | Traction power supply: substations | 0
50.04 | Traction power distribution: catenary and third rail | 0
50.05 | Communications | 2553142.2806
50.06 | Fare collection system and equipment | 5599501.1738
50.07 | Central Control | 243776.3792
Construction Subtotal (10 - 50) |  | 148439278.7678
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 8317315.3259
60.01 | Purchase or lease of real estate | 8317315.3259
60.02 | Relocation of existing households and businesses | 0
70 VEHICLES (number) |  | 28933559.1132
70.01 | Light Rail | 0
70.02 | Heavy Rail | 0
70.03 | Commuter Rail | 0
70.04 | Bus | 28761221.2452
70.05 | Other | 172337.868
70.06 | Non-revenue vehicles | 0
70.07 | Spare parts | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | 42496643.2991
80.01 | Project Development | 25668157.3431
80.02 | Engineering (not applicable to Small Starts) | 0
80.03 | Project Management for Design and Construction | 2803708.092
80.04 | Construction Administration & Management | 11221069.7719
80.05 | Professional Liability and other Non-Construction Insurance | 700927.023
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | 700927.023
80.07 | Surveys, Testing, Investigation, Inspection | 700927.023
80.08 | Start up | 700927.023
Subtotal (10 - 80) |  | 228186796.5059
90 UNALLOCATED CONTINGENCY |  | 21717799.3136
Subtotal (10 - 90) |  | 249904595.8195
100 FINANCE CHARGES |  | 0
Total Project Cost (10 - 100) |  | 249904595.8195
Note on B1: This sheet, SSGA A3T1, and the sheets that follow become Attachments to the SSGA
Note on B3: Delete rows that are not needed.

## SSGA A3T2
Table 2 - Inflated Cost to Year of Expenditure
| Base Year Dollars w/o Contingency (X000) | Base Year Dollars Allocated Contingency (X000) | Base Year Dollars TOTAL (X000) | Inflation Factor | YOE Dollars TOTAL (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 29226452.64 | 3117231.9 | 32343684.54 | 1.1236 | 36341075.2531
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 13385987.01 | 1380036.23 | 14766023.24 | 1.1273 | 16645468.6597
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 8134642.34 | 1188130.59 | 9322772.93 | 1.1607 | 10820574.0263
40 SITEWORK & SPECIAL CONDITIONS | 50306479.43 | 3919572.48 | 54226051.91 | 1.1244 | 60969971.2519
50 SYSTEMS | 18883333.9 | 1888333.39 | 20771667.29 | 1.1392 | 23662189.5767
60 ROW, LAND, EXISTING IMPROVEMENTS | 5597955.84 | 2239182.34 | 7837138.18 | 1.0613 | 8317315.3259
70 VEHICLES (number) | 24821818.1 | 361468.18 | 25183286.28 | 1.1489 | 28933559.1132
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 39842538.13 | 0 | 39842538.13 | 1.0666 | 42496643.2991
90 UNALLOCATED CONTINGENCY |  |  | 17925987.62 | 1.2115 | 21717799.3136
100 FINANCE CHARGES |  |  | 0 | #DIV/0! | 0
Total Project Cost (10 - 100) |  |  | 222219150.12 | 1.1246 | 249904595.8195
Note on G3: Delete rows that are not needed.

## A3T3
Table 3 - BCE by Source of Funding
| Total Project Cost in YOE Dollars (X000) | Double Check Total (X000) | Federal 5309 Small Starts | Federal Other | Local
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 36341075.2531 | 36341075.2531 | 7433789.2329 | 20000000 | 8907286.0203
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 16645468.6597 | 16645468.6597 | 7813831.1669 | 0 | 8831637.4928
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10820574.0263 | 10820574.0263 | 5954928.1042 | 0 | 4865645.9221
40 SITEWORK & SPECIAL CONDITIONS | 60969971.2519 | 60969971.2519 | 10892373.5518 | 34400000 | 15677597.7002
50 SYSTEMS | 23662189.5767 | 23662189.5767 | 4085390.5906 | 7565760 | 12011038.9861
60 ROW, LAND, EXISTING IMPROVEMENTS | 8317315.3259 | 8317315.3259 | 1651930.0998 | 0 | 6665385.2261
70 VEHICLES (number) | 28933559.1132 | 28933559.1132 | 21146847.2906 | 0 | 7786711.8226
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 42496643.2991 | 42496643.2991 | 21326139.8352 | 0 | 21170503.4639
90 UNALLOCATED CONTINGENCY | 21717799.3136 | 21717799.3141 | 19644770.1281 | 0 | 2073029.1859
100 FINANCE CHARGES | 0 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 249904595.8195 | 249904595.82 | 99950000 | 61965760 | 87988835.82
Sources of Federal Funding and Matching Share Ratios
| Costs Attributed to Source of Funds (X000) | Federal/ Local Matching Ratio within Source | All Federal Funds (X000) | Local Funds (X000)
Federal 5309 New Starts | 0
Federal Other (please specify sources...) | 0
Total | 0 |  | 0 | 0
Overall Federal Share of Project |  |  | #DIV/0!
New Starts Share of Project |  |  | 40%
Note on F2: Add columns as required to show all federal funding.
Note on A3: Delete rows that are not needed.
Note on A19: Add rows as needed to show all federal funding.

## A3A
Scope and Activity Description
Scope Code | ALI Code | Scope and Activity Line Item Descriptions | Qty |  | Federal 5309 Small Starts |  |  | Federal Other |  |  | Project Totals |  |  | Check Total Project Cost in YOE Dollars (X000)
|  |  |  | Total Federal % | Federal | Local | Total | Federal | Local | Total | Federal | Local | Total
14010 | 140110 | GUIDEWAY & TRACK ELEMENTS | 14.95 | #DIV/0! |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 36341075.2531
14020 | 140220 | STATIONS, STOPS, TERMINALS, INTERMODAL | 46 | #DIV/0! |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 16645468.6597
14030 | 140330 | SUPPORT FACILITIES, YARDS, SHOPS, ADMIN. BLDGS. |  | #DIV/0! |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 10820574.0263
14040 | 140440 | SITEWORK & SPECIAL CONDITIONS |  | #DIV/0! |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 60969971.2519
14050 | 140550 | SYSTEMS |  | #DIV/0! |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 23662189.5767
14060 | 140660 | ROW, LAND, EXISTING IMPROVEMENTS |  | #DIV/0! |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 8317315.3259
14070 |  | VEHICLES | 67 | #DIV/0! |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 28933559.1132
| 13.13.20 | Light Rail Cars
13.__.__
14080 | 140880 | PROFESSIONAL SERVICES |  | #DIV/0! |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 42496643.2991
14090 | 140990 | UNALLOCATED CONTINGENCY |  | #DIV/0! |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 21717799.3136
14100 | 141010 | FINANCE CHARGES |  | #DIV/0! |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) |  |  |  | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249904595.8195
Note on I2: Add more tri-columns as required to show all funding.
Note on C4: Delete rows that are not needed.

## A4
SCHEDULE | Start Date | End Date | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 2021-03-30 | 2024-07-26
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 2021-03-30 | 2024-07-26
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 2021-03-30 | 2024-07-26
40 SITEWORK & SPECIAL CONDITIONS | 2021-03-30 | 2024-07-26
50 SYSTEMS | 2021-03-30 | 2024-07-26
60 ROW, LAND, EXISTING IMPROVEMENTS | 2019-10-01 | 2022-08-31
70 VEHICLES (number) | 2022-03-21 | 2023-07-21
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 2017-06-01 | 2025-05-30
90 UNALLOCATED CONTINGENCY | 2024-09-06 | 2025-05-30
100 FINANCE CHARGES | 0 | 0
REVENUE OPERATIONS | 2024-09-06 | 0
Note on D1: Delete unnecessary columns.
Note on A2: Delete rows that are not needed.