## ConstructionPivotTable
SCC Code | Sum of Total Cost
10.02 | 22192550.4336
20.01 | 13080635
30.02 | 8332766.4593
40.01 | 260931.742
40.02 | 4384298.6016
40.03 | 45000
40.06 | 10052128.3549
50.02 | 24984353.25
50.05 | 3013087.0149
50.06 | 12261000
70.04 | 33486039
Construction + Vehicles | 132092789.8563
60 | 1254737
80 | 24959223.4341
80.01 | 2770772
80.03 | 9860675.0856
80.04 | 10098675.0856
80.05 | 493033.7543
80.06 | 493033.7543
80.07 | 493033.7543
80.08 | 750000
Construction | 98606750.8563
Vehicles | 33486039
ROW | 1254737
Professional Services | 24959223.4341
Allocated Contingency | 14791012.6284
Unallocated Contingency | 4099059.9535
Total Contingency (Construction Basis) | 18890072.582
Non-Construction Contingency | 1569756.6617
Mellon Terrace + Move Station Contingency | 0
Allocated Contingency % | 15%
Unallocated Contingency % | 4.157%
Standard Construction Basis Contingency | 19.16%
Mellon Terrace + Move Station Contingency % | 0%
Total Contingency % | 19.16%
Inflation Rate | 3%
Inflation Cost | 16733420.6837
Total Cost (YOE) | 195500000.2178
Check | 195500000.2178

## SCC List
Standard Cost Categories for Small Starts Projects
(Rev.19, June 2017)
10 GUIDEWAY & TRACK ELEMENTS (route miles)
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure
10.05 | Guideway: Built-up fill
10.06 | Guideway: Underground cut & cover
10.07 | Guideway: Underground tunnel
10.08 | Guideway: Retained cut or fill
10.09 | Track: Direct fixation
10.1 | Track: Embedded
10.11 | Track: Ballasted
10.12 | Track: Special (switches, turnouts)
10.13 | Track: Vibration and noise dampening
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform
20.03 | Underground station, stop, shelter, mall, terminal, platform
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development
20.06 | Automobile parking multi-story structure
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility
30.03 | Heavy Maintenance Facility
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track
40 SITEWORK & SPECIAL CONDITIONS
40.01 | Demolition, Clearing, Earthwork
40.02 | Site Utilities, Utility Relocation
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping
40.07 | Automobile, bus, van accessways including roads, parking lots
40.08 | Temporary Facilities and other indirect costs during construction
50 SYSTEMS
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications
50.06 | Fare collection system and equipment
50.07 | Central Control
60 ROW, LAND, EXISTING IMPROVEMENTS
60.01 | Purchase or lease of real estate
60.02 | Relocation of existing households and businesses
70 VEHICLES (number)
70.01 | Light Rail
70.02 | Heavy Rail
70.03 | Commuter Rail
70.04 | Bus
70.05 | Other
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
80.01 | Project Development
80.02 | Engineering (not applicable to Small Starts)
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Professional Liability and other Non-Construction Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up
90 UNALLOCATED CONTINGENCY
100 FINANCE CHARGES

## SCC Definitions
Standard Cost Categories for Small Starts Projects D E F I N I T I O N S |  | NOTE: The SCC cost breakdown is based on a traditional Design Bid Build model. If your project is Design Build, to the best of your ability, separate construction costs from design, administration, testing, etc. Put all construction costs in 10 through 50. Put design, administration, testing, etc. in 80 Professional Services.
(Rev.19, June 2017)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | Include guideway and track costs for all transit modes (heavy rail, light rail, commuter rail, BRT, rapid bus, bus, monorail, cable car, etc.) The unit of measure is route miles of guideway, regardless of width. As associated with the guideway, include costs for rough grading, excavation, and concrete base for guideway where applicable. Include all construction materials and labor regardless of whom is performing the work. In your written description of the scope, and in supporting graphic diagrams, indicate whether busway or rail track is single, double, triple, relocated, etc. Put guideway and track elements associated with yards in 30 Support Facilities below.
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure | Include foundation excavation; guideway structures including caissons, columns, bridges, viaducts, cross-overs, fly-overs.
10.05 | Guideway: Built-up fill | Include construction of earthen berms.
10.06 | Guideway: Underground cut & cover | Include excavation, retaining walls, backfill, underground guideway structure and finishes.
10.07 | Guideway: Underground tunnel | Include tunneling by means of a tunnel boring machine, drill blasting, mining, and immersed tube tunneling; tunnel structure and finishes.
10.08 | Guideway: Retained cut or fill | Include excavation, retaining walls, backfill, underground guideway structure and finishes.
10.09 | Track: Direct fixation | Include rails, connectors.
10.1 | Track: Embedded | Include rails, ties; ballast where applicable
10.11 | Track: Ballasted | Include rails, ties and ballast.
10.12 | Track: Special (switches, turnouts) | Include transitional curves.
10.13 | Track: Vibration and noise dampening | Include upcharge for vib/noise dampening to any track condition above.
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | As associated with stations, include costs for rough grading, excavation, station structures, enclosures, finishes, equipment; mechanical and electrical components including HVAC, ventilation shafts and equipment, station power, lighting, public address/customer information system, safety systems such as fire detection and prevention, security surveillance, access control, life safety systems, etc. Include all construction materials and labor regardless of whom is performing the work. NOTE: Count paired inbound/outbound boarding platforms as one station - do not report the total number of boarding platforms.
Put guideway and track associated with stations in 10 Guideway & Track Elements above.
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform | Include station structures including caissons, columns, platforms, superstructures, etc.
20.03 | Underground station, stop, shelter, mall, terminal, platform | Include retaining walls, backfill, structure.
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development | Per FTA's Joint Development Guidance, "Joint development is any income-producing activity with a transit nexus related to a real estate asset in which FTA has an interest. ...Joint development projects are commercial, residential, industrial, or mixed-use developments that are induced by or enhance the effectiveness of transit projects. . ."
20.06 | Automobile parking multi-story structure | Include retaining walls, backfill, structure.
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | As associated with support facilities, include costs for rough grading, excavation, support structures, enclosures, finishes, equipment; mechanical and electrical components including HVAC, ventilation shafts and equipment, facility power, lighting, public address system, safety systems such as fire detection and prevention, security surveillance, access control, life safety systems, etc. Include fueling stations. Include all construction materials and labor regardless of whom is performing the work.
Where a support facility shares the structure with a station, its cost may be included with station cost. Identify this with a note.
Except for guideway and track associated with a yard, include all guideway and track costs associated with support facilities in 10 Guideway & Track Elements above.
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility | Include service, inspection, and storage facilities and equipment.
30.03 | Heavy Maintenance Facility | Include heavy maintenance and overhaul facilities and equipment.
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track | Include yard construction, guideway and track associated with yard.
40 SITEWORK & SPECIAL CONDITIONS |  | Include all construction materials and labor regardless of whom is performing the work.
40.01 | Demolition, Clearing, Earthwork | Include project-wide clearing, demolition and fine grading.
40.02 | Site Utilities, Utility Relocation | Include all site utilities - storm, sewer, water, gas, electric.
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | Include underground storage tanks, fuel tanks, other hazardous materials and treatments, etc.
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | Include other environmental mitigation not listed.
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping | Include sidewalks, paths, plazas, functional landscaping, site and station furniture, site lighting, signage, bike facilities, permanent fencing.
40.07 | Automobile, bus, van accessways including roads, parking lots | Include all on-grade paving.
40.08 | Temporary Facilities and other indirect costs during construction | As a general rule and to the extent possible, appropriately allocate indirect costs among the construction costs in Categories 10 through 50. Where that is not possible, include in 40.08 Temporary Facilities costs for mobilization, demobilization, phasing; time and temporary construction associated with weather (heat, rain, freezing, etc.); temporary power and facilities; temporary construction, easements, and barriers for storm water pollution prevention, temporary access and to mitigate construction impacts; project and construction supervision; general conditions, overhead, profit. NOTE: Include contractor's general liability and other insurance related to construction such as builder's risk in Cats. 10 - 50, not in 80 Professional Services below.
50 SYSTEMS |  | Include all construction materials and labor regardless of whom is performing the work.
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection | Include signal prioritization at intersections.
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications | Include passenger information systems at stations and on vehicles (real time travel information; static maps and schedules). Include equipment to allow communications among vehicles and with central control.
50.06 | Fare collection system and equipment | Include fare sales and swipe machines, fare counting equipment.
50.07 | Central Control
Construction Subtotal (10 - 50)
60 ROW, LAND, EXISTING IMPROVEMENTS |  | Include professional services associated with the real estate component of the project. These costs may include agency staff oversight and administration, real estate and relocation consultants, legal counsel, court expenses, insurance, etc.
60.01 | Purchase or lease of real estate | If the value of right-of-way, land, and existing improvements is to be used as local match to the Federal funding of the project, include the total cost on this line item. In backup documentation, separate cost for land from cost for improvements. Identify whether items are leased, purchased or acquired through payment or for free. Include the costs for permanent surface and subsurface easements, trackage rights, etc.
60.02 | Relocation of existing households and businesses | In compliance with Uniform Relocation Act.
70 VEHICLES (number) |  | Include professional services associated with the vehicle component of the project. These costs may include agency staff oversight and administration, vehicle consultants, design and manufacturing contractors, legal counsel, warranty and insurance costs, etc.
70.01 | Light Rail | Include light rail and streetcar rail using electric, diesel or other power supply.
70.02 | Heavy Rail
70.03 | Commuter Rail | Include locomotives (diesel, electric, or other), trailer cars, self-propelled multiple units (EMU electric or DMU diesel, or other power supply)
70.04 | Bus | Includes "rubber-tired" buses and trolleys including new, used, historic replica, articulated, using electric, diesel, dual-power, or other power supply.
70.05 | Other | Include Vans, Sedan/Station Wagon, Cable Car, People Mover, Monorail, Car/Inclined Railway, Ferry Boat, Transferred Vehicle
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | Cat. 80 applies to Cats. 10-50. Cat. 80 includes all professional, technical and management services related to the design and construction of fixed infrastructure (Cats. 10 - 50) during the project development and construction phases of the project. This includes environmental work, design, engineering and architectural services; specialty services such as safety or security analyses; value engineering, risk assessment, cost estimating, scheduling, ridership modeling and analyses, auditing, legal services, administration and management, etc. by agency staff or outside consultants. Include professional liability insurance and other non-construction insurance on 80.05 unless insurance for the agency and its consultants is already included in other lines. Include costs associated with professional services related to real estate and vehicles in Cats. 60 and 70. (Note that costs for planning activities and NEPA work done before FTA approval to enter project development (PD), regardless of funding source, are not included in an SSGA and therefore, should not be included in the Standard Cost Category worksheets. For example, on one and the same grant, costs incurred prior to FTA approval to enter PD should be omitted from these worksheets whereas costs incurred after FTA approval to enter PD should be included.)
80.01 | Project Development
80.02 | Engineering (not applicable to Small Starts)
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Professional Liability and other Non-Construction Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up | Include start up and training. Include in Cats. 10 - 50 above access and protection work by agency staff or outside contractors.
Subtotal (10 - 80)
90 UNALLOCATED CONTINGENCY |  | Includes unallocated contingency, project reserves. Document allocated contingencies for individual line items on the BUILD Main worksheet.
Subtotal (10 - 90)
100 FINANCE CHARGES |  | Include finance charges expected to be paid by the project sponsor/grantee prior to either the completion of the project or the fulfillment of the Small Starts funding commitment, whichever occurs later in time. Finance charges incurred after this date should not be included in Total Project Cost. (See FFGA Circular FTA C5200.1A Chapter III for additional information.) Derive finance charges from the Small Starts project's financial plan, based on an analysis of the sources and uses of funds. The amount and type of debt financing required and revenues available determine the finance charges. By year, compute finance charges in year-of-expenditure (YOE) dollars. On the Inflation worksheet enter the finance charges for the appropriate years.
Total Project Cost (10 - 100)

## TrAMS Scopes ALIs
14-Series TrAMS Scope / Activity Line Items Required for all grants that serve a Capital Project
(Rev.19, June 2017)
1. HOW DO THE SCC AND TrAMS RELATE? TrAMS is for grants management. Many grants can serve a capital project -- e.g. CMAQ, 5307, 5309, etc. The Standard Cost Categories (SCC) are for cost management, day to day as well as at important milestones. To manage capital project costs use the SCC worksheets, back up sheets, detailed cost estimates, etc. At important milestones, "paperclip" the SCC worksheets to the applicable grants in TrAMS. TrAMS and the SCC support each other but TrAMS doesn't duplicate the level of information in the SCC. Grant budgets will have just the ten lines. 2. WHEN SHOULD I USE THE 14-SERIES? Use it for capital projects. For a New Starts project, use it from the very first grant that funds Project Development, and include all grants issued through the FFGA; these grants may be small or large and may derive funding from diverse sources such as CMAQ, 5307, 5309 New Starts, Federal Non-Transportation funding from HUD, Defense, etc. 3. HOW IS THE 14-SERIES ORGANIZED AND WHY? The 14-Series has one Scope and 10 ALIs. The organization is intentionally simple. Put guideway costs under the Guideway ALI, station costs under the Station ALI. If the costs are organized simply, the information will be consistent program-wide and will produce a reliable database. For Vehicles, use the 13-Series ALIs. | 140-00 | PROJECT NAME - (this is the one Scope)
| 14.01.10 | GUIDEWAY & TRACK ELEMENTS |  | .01 Bus STD 40 FT
.02 Bus STD 35 FT
.03 Bus 30 FT
| 14.02.20 | STATIONS, STOPS, TERMINALS, INTERMODAL |  | .04 Bus < 30 FT
.05 Bus School
.06 Bus Articulated
| 14.03.30 | SUPPORT FACILITIES: YARDS, SHOPS, ADMIN BLDGS |  | .07 Bus Commuter / Suburban
.08 Bus Intercity
.09 Bus Trolley STD
| 14.04.40 | SITEWORK & SPECIAL CONDITIONS | Engineering & Design | .10 Bus Trolley Artic.
|  |  | 13.11.XX | .11 Bus Double Deck
.12 Bus Used
| 14.05.50 | SYSTEMS | Purchase - Replacement | .13 Bus School Used
|  |  | 13.12.XX | .14 Bus Dual Mode
.15 Vans
| 14.06.60 | ROW, LAND, EXISTING IMPROVEMENTS | Purchase - Expansion | .16 Sedan / Station Wagon
|  |  | 13.13.XX | .20 Light Rail Cars
.21 Heavy Rail Cars
| 13____ | VEHICLES - use the 13-Series ALIs for vehicles. | Rehabilitation / Rebuild | .22 Commuter Rail Self Propelled Electric
|  |  | 13.14.XX | .23 Commuter Rail Car Trailer
.24 Commuter Rail Locomotive Diesel
| 14.08.80 | PROFESSIONAL SERVICES | Mid Life Rebuild (Rail) | .25 Commuter Rail Locomotive Electric
|  |  | 13.15.XX | .26 Commuter Rail Cars Used
.27 Commuter Rail Locomotive Used
| 14.09.90 | UNALLOCATED CONTINGENCY | Lease - Replacement | .28 Commuter Rail Self Propelled - Diesel
|  |  | 13.16.XX | .30 Cable Car
.31 People Mover
| 14.10.10 | FINANCE CHARGES | Lease - Expansion | .32 Car, Incline Railway
|  |  | 13.18.XX | .33 Ferry Boats
.39 Transferred Vehicles
|  |  | Vehicle Overhaul | .40 Spare Parts/Assoc.Capital
|  |  | 13.17.00 | / Maintenance Items

## BUILD Main
M A I N W O R K S H E E T - B U I L D A L T E R N A T I V E | [8 empty] | (Rev.19, June 2017)
Urban Redevelopment Authority of Pittsburgh (URA) | [6 empty] | Today's Date |  | 2019-03-12 11:30
Downtown-Uptown-Oakland-East End Bus Rapid Transit | [6 empty] | Yr of Base Year $ |  | 2018
Application to enter the President's FY2020 Budget | [6 empty] | Yr of Revenue Ops |  | 2021
|  | Quantity | Base Year Dollars w/o Contingency (X000) | Base Year Dollars Allocated Contingency (X000) | Base Year Dollars TOTAL (X000) | Base Year Dollars Unit Cost (X000) | Base Year Dollars Percentage of Construction Cost | Base Year Dollars Percentage of Total Project Cost | YOE Dollars Total (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 10.45 | 22192550.4336 | 3328882.565 | 25521432.9987 | 2442242.3922 | 22.51% | 14.28% | 27890395.7283 | 1.0928
10.01 | Guideway: At-grade exclusive right-of-way |  |  |  | 0 |  |  |  | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 10.45 | 22192550.4336 | 3328882.565 | 25521432.9987 | 2442242.3922 |  |  | 27890395.7283
10.03 | Guideway: At-grade in mixed traffic |  |  |  | 0 |  |  |  | 0
10.04 | Guideway: Aerial structure |  |  |  | 0 |  |  |  | 0
10.05 | Guideway: Built-up fill |  |  |  | 0 |  |  |  | 0
10.06 | Guideway: Underground cut & cover |  |  |  | 0 |  |  |  | 0
10.07 | Guideway: Underground tunnel |  |  |  | 0 |  |  |  | 0
10.08 | Guideway: Retained cut or fill |  |  |  | 0 |  |  |  | 0
10.09 | Track: Direct fixation |  |  |  | 0 |  |  |  | 0
10.1 | Track: Embedded |  |  |  | 0 |  |  |  | 0
10.11 | Track: Ballasted |  |  |  | 0 |  |  |  | 0
10.12 | Track: Special (switches, turnouts) |  |  |  | 0 |  |  |  | 0
10.13 | Track: Vibration and noise dampening |  |  |  | 0 |  |  |  | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 44 | 13080635 | 1962095.25 | 15042730.25 | 341880.233 | 13.27% | 8.415% | 16537659.3778 | 1.0994
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 44 | 13080635 | 1962095.25 | 15042730.25 | 341880.233 |  |  | 16537659.3778
20.02 | Aerial station, stop, shelter, mall, terminal, platform |  |  |  | 0 |  |  |  | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform |  |  |  | 0 |  |  |  | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. |  |  |  | 0 |  |  |  | 0
20.05 | Joint development |  |  |  | 0 |  |  |  | 0
20.06 | Automobile parking multi-story structure |  |  |  | 0 |  |  |  | 0
20.07 | Elevators, escalators |  |  |  | 0 |  |  |  | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 10.45 | 8332766.4593 | 1249914.9689 | 9582681.4281 | 917003.0075 | 8.451% | 5.36% | 10534997.2213 | 1.0994
30.01 | Administration Building: Office, sales, storage, revenue counting |  |  |  | 0 |  |  |  | 0
30.02 | Light Maintenance Facility |  | 8332766.4593 | 1249914.9689 | 9582681.4281 |  |  |  | 10534997.2213
30.03 | Heavy Maintenance Facility |  |  |  | 0 |  |  |  | 0
30.04 | Storage or Maintenance of Way Building |  |  |  | 0 |  |  |  | 0
30.05 | Yard and Yard Track |  |  |  | 0 |  |  |  | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 10.45 | 14742358.6985 | 2211353.8048 | 16953712.5032 | 1622364.8328 | 14.95% | 9.484% | 18582975.4981 | 1.0961
40.01 | Demolition, Clearing, Earthwork |  | 260931.742 | 39139.7613 | 300071.5033 |  |  |  | 328908.5734
40.02 | Site Utilities, Utility Relocation |  | 4384298.6016 | 657644.7902 | 5041943.3918 |  |  |  | 5526477.4896
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  | 45000 | 6750 | 51750 |  |  |  | 56723.2093
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  |  |  | 0 |  |  |  | 0
40.05 | Site structures including retaining walls, sound walls |  |  |  | 0 |  |  |  | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 10052128.3549 | 1507819.2532 | 11559947.6081 |  |  |  | 12670866.2259
40.07 | Automobile, bus, van accessways including roads, parking lots |  |  |  | 0 |  |  |  | 0
40.08 | Temporary Facilities and other indirect costs during construction |  |  |  | 0 |  |  |  | 0
50 SYSTEMS |  | 10.45 | 40258440.2649 | 6038766.0397 | 46297206.3047 | 4430354.6703 | 40.83% | 25.9% | 51197289.8419 | 1.1058
50.01 | Train control and signals |  |  |  | 0 |  |  |  | 0
50.02 | Traffic signals and crossing protection |  | 24984353.25 | 3747652.9875 | 28732006.2375 |  |  |  | 31772993.8476
50.03 | Traction power supply: substations |  |  |  | 0 |  |  |  | 0
50.04 | Traction power distribution: catenary and third rail |  |  |  | 0 |  |  |  | 0
50.05 | Communications |  | 3013087.0149 | 451963.0522 | 3465050.0672 |  |  |  | 3831790.0099
50.06 | Fare collection system and equipment |  | 12261000 | 1839150 | 14100150 |  |  |  | 15592505.9844
50.07 | Central Control |  |  |  | 0 |  |  |  | 0
Construction Subtotal (10 - 50) |  | 10.45 | 98606750.8563 | 14791012.6284 | 113397763.4847 | 10851460.6205 | 100% | 63.43% | 124743317.6675
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 10.45 | 1254737 | 125473.7 | 1380210.7 | 132077.5789 |  | 0.7721% | 1464265.5316 | 1.0609
60.01 | Purchase or lease of real estate |  | 1254737 | 125473.7 | 1380210.7 |  |  |  | 1464265.5316
60.02 | Relocation of existing households and businesses |  |  |  | 0 |  |  |  | 0
70 VEHICLES (number) |  | 25 | 33486039 | 334860.39 | 33820899.39 | 1352835.9756 |  | 18.92% | 36965083.061 | 1.093
70.01 | Light Rail |  |  |  | 0 |  |  |  | 0
70.02 | Heavy Rail |  |  |  | 0 |  |  |  | 0
70.03 | Commuter Rail |  |  |  | 0 |  |  |  | 0
70.04 | Bus | 25 | 33486039 | 334860.39 | 33820899.39 | 1352835.9756 |  |  | 36965083.061
70.05 | Other |  |  |  | 0 |  |  |  | 0
70.06 | Non-revenue vehicles |  |  |  | 0 |  |  |  | 0
70.07 | Spare parts |  |  |  | 0 |  |  |  | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | 10.45 | 24959223.4341 | 1109422.5717 | 26068646.0058 | 2494607.2733 | 22.99% | 14.58% | 27780993.1696 | 1.0657
80.01 | Project Development |  | 2770772 |  | 2770772 |  |  |  | 2952773.1509
80.02 | Engineering (not applicable to Small Starts)
80.03 | Project Management for Design and Construction |  | 9860675.0856 | 493033.7543 | 10353708.8399 |  |  |  | 11033803.3858
80.04 | Construction Administration & Management |  | 10098675.0856 | 504933.7543 | 10603608.8399 |  |  |  | 11300118.3371
80.05 | Professional Liability and other Non-Construction Insurance |  | 493033.7543 | 24651.6877 | 517685.442 |  |  |  | 551690.1693
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 493033.7543 | 24651.6877 | 517685.442 |  |  |  | 551690.1693
80.07 | Surveys, Testing, Investigation, Inspection |  | 493033.7543 | 24651.6877 | 517685.442 |  |  |  | 551690.1693
80.08 | Start up |  | 750000 | 37500 | 787500 |  |  |  | 839227.7879
Subtotal (10 - 80) |  | 10.45 | 158306750.2904 | 16360769.2901 | 174667519.5805 | 16714595.1752 |  | 97.71% | 190953659.4297
90 UNALLOCATED CONTINGENCY |  |  |  |  | 4099059.9535 |  |  | 2.293% | 4546340.7881 | 1.1091
Subtotal (10 - 90) |  | 10.45 |  |  | 178766579.5341 | 17106849.7162 |  | 100% | 195500000.2178
100 FINANCE CHARGES |  |  |  |  | 0 |  |  | 0% | 0 | #DIV/0!
Total Project Cost (10 - 100) |  | 10.45 |  |  | 178766579.5341 | 17106849.7162 |  | 100% | 195500000.2178 | 1.0936
Allocated Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 10.33%
Unallocated Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 2.589%
Total Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 12.92%
Unallocated Contingency as % of Subtotal (10 - 80) |  |  |  |  | 2.347%
YOE Construction Cost per Mile (X000) | [8 empty] | 11937159.5854
YOE Total Project Cost per Mile Not Including Vehicles (X000) | [8 empty] | 15170805.4696
YOE Total Project Cost per Mile (X000) | [8 empty] | 18708133.9921
Note on J3: Year of Base Year Dollars should match the year in "Today's Date."
Note on J6: YOE Dollars automatically arrive from Inflation Worksheet.
Note on D8: For all cells, enter costs to the nearest $1. Note, all costs will be displayed to the nearest $1,000!
Note on J8: YOE costs for individual line items within a Category are derived as a percentage of the YOE cost of the Category.
Note on I19: Preparing for bid: For each separate contract package generate a Main Worksheet and an Inflation Worksheet. In the Special Conditions of the Contract, require the construction contractor to update these worksheets and submit them with the monthly pay application. This should make it easy to track costs in the SCC format throughout construction, and make it easy to submit the final costs to FTA at contract closeout.
Note on F76: Enter finance charges on Inflation Worksheet.

## Inflation
I N F L A T I O N W O R K S H E E T |  |  |  |  | (Rev.19, June 2017)
Urban Redevelopment Authority of Pittsburgh (URA) |  |  | Today's Date |  | 2019-03-12 11:30
Downtown-Uptown-Oakland-East End Bus Rapid Transit |  |  | Yr of Base Year $ |  | 2018
Application to enter the President's FY2020 Budget |  |  | Yr of Revenue Ops |  | 2021
Insert comments, notes, etc.
BASE YEAR DOLLARS (X$000) | Base Yr Dollars | Double-Check Total | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 25521432.9987 | 25521432.9987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2552143.2999 | 20417146.399 | 2552143.2999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 15042730.25 | 15042730.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1504273.025 | 9025638.15 | 4512819.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 9582681.4281 | 9582681.4281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 958268.1428 | 5749608.8569 | 2874804.4284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 16953712.5032 | 16953712.5032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1695371.2503 | 11867598.7523 | 3390742.5006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS | 46297206.3047 | 46297206.3047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27778323.7828 | 18518882.5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 1380210.7 | 1380210.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380210.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number) | 33820899.39 | 33820899.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8455224.8475 | 16910449.695 | 8455224.8475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 26068646.0058 | 26068646.0058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2770772 | 6517161.5015 | 6517161.5015 | 5131775.5015 | 5131775.5015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 4099059.9535 | 4099059.9535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2049529.9768 | 2049529.9768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 FINANCE CHARGES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 178766579.5341 | 178766579.5341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2770772 | 6517161.5015 | 23062652.767 | 98930071.1141 | 47485922.1515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inflation Rate |  |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03
Compounded Inflation Factor |  |  | 1.3439 | 1.3048 | 1.2668 | 1.2299 | 1.1941 | 1.1593 | 1.1255 | 1.0927 | 1.0609 | 1.03 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 1.4685 | 1.5126 | 1.558 | 1.6047 | 1.6528 | 1.7024 | 1.7535 | 1.8061
YEAR OF EXPENDITURE DOLLARS (X$000) | YOE Dollars |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 27890395.7283 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2707568.8268 | 22310367.1331 | 2872459.7684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 16537659.3778 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1595883.2522 | 9862558.4987 | 5079217.6268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10534997.2213 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016626.6727 | 6282752.8374 | 3235617.7112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 18582975.4981 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1798619.3595 | 12968045.5818 | 3816310.5569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS | 51197289.8419 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30354124.4122 | 20843165.4297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 1464265.5316 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1464265.5316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number) | 36965083.061 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8970148.0407 | 18478504.9639 | 9516430.0564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 27780993.1696 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2770772 | 6712676.3465 | 6914056.6369 | 5607629.6484 | 5775858.5378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 4546340.7881 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2239576.7429 | 2306764.0452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 FINANCE CHARGES | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 195500000.2178 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2770772 | 6712676.3465 | 24467168.3205 | 108103559.8183 | 53445823.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on K8: Because of inflation, it costs more to buy the same goods and services today than it would have cost in previous years. The total base year dollar cost is a concept that represents the total project cost if the project were planned, designed and built in only one year, the designated base year.
Note on O8: In the white cells, insert project costs in the year in which they occurred (lower rows) or are planned to occur (upper rows) through the completion of the project or the fulfillment of the New Starts funding commitment, whichever is expected to occur later in time.
Note on O21: In the Base Year no inflation multiplier is used.
Note on E24: For past years, enter the actual dollars spent in each year. The dollars will inflate when converted to the current base year.
Note on E33: Enter Finance Charges on this line.

## Project Description
P R O J E C T D E S C R I P T I O N - B U I L D A L T E R N A T I V E |  |  |  | (Rev.19, June 2017)
Urban Redevelopment Authority of Pittsburgh (URA) |  |  | Today's Date | 2019-03-12 11:30
Downtown-Uptown-Oakland-East End Bus Rapid Transit
Application to enter the President's FY2020 Budget
Describe the project elements to explain the unit costs shown on the Main Worksheet. Example: A 20-mile new light rail project has its guideway entirely on grade except for a one-eighth mile bridge over a river. The bridge or aerial structure may have a relatively high unit cost because there is little economy of scale. Mention precedents and reference points used in the development of costs for this project. Mention other aspects of this project that were important considerations in estimating costs. These could include the physical context, site constraints; design parameters; institutional, contracting and procurement conditions; project schedule, etc.
10 GUIDEWAY & TRACK ELEMENTS (route miles)
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | Pavement marking and signing within Downtown, complete roadway reconstruction within Uptown, and a mix of roadway reconstruction and pavement marking and signing within Oakland. Within Downtown-Uptown-Oakland, there will be dedicated BRT only lanes. A 15% allocated contingency is used.
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure
10.05 | Guideway: Built-up fill
10.06 | Guideway: Underground cut & cover
10.07 | Guideway: Underground tunnel
10.08 | Guideway: Retained cut or fill
10.09 | Track: Direct fixation
10.1 | Track: Embedded
10.11 | Track: Ballasted
10.12 | Track: Special (switches, turnouts)
10.13 | Track: Vibration and noise dampening
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
20.01 | At-grade station, stop, shelter, mall, terminal, platform | Includes 43 enhanced/branded station pairs at 72 platforms. Three primary station types are planned: Neighborhood, Intermediate, and Transit Center. The stations would range in size from a length of 15-feet (Neighborhood), 30-feet or 60 feet (Intermediate) and 120-feet (Transit Center), with a platform width approximately 10-feet wide. The proposed locations of stations are based on existing bus stops, ridership, intersection locations, and corridor activity generators. A typical station would consist of a platform with shelter, passenger seating, signage, real-time passenger information, ticket vending machines for improved fare collection, and trash receptacles. A 15% allocated contingency is used.
20.02 | Aerial station, stop, shelter, mall, terminal, platform
20.03 | Underground station, stop, shelter, mall, terminal, platform
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development
20.06 | Automobile parking multi-story structure
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility | Three overhead in-line charging stations and the addition of "plug-in" charging units at the maintenance facility are provided. Three comfort stations are also planned with one in Oakland, one at the end of the Highland Park branch and one at the end of the Squirrel Hill branch. A 15% allocated contingency is used.
30.03 | Heavy Maintenance Facility
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track
40 SITEWORK & SPECIAL CONDITIONS
40.01 | Demolition, Clearing, Earthwork | Includes demolition/removal/clearing for roadway construction. Demolition/Clearing for the stations and maintenance facility aree included in their respective SCC code. A 15% allocated contingency is used.
40.02 | Site Utilities, Utility Relocation | Includes cost for vault replacements and adjustment of utilities throughout the corridor. Miscellanious cost is also include for waterline and gas line replacments in uptown. A 15% allocated contingency is used.
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | Includes costs for water pollution control along any sections with roadway reconstruction. A 15% allocated contingency is used.
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping | Includes new sidewalk, pedestrian/bicycle amenities, and landscaping elements along roadways with reconstruction. ADA ramp costs are also included in this category at the signal locations. A 15% allocated contingency is used.
40.07 | Automobile, bus, van accessways including roads, parking lots
40.08 | Temporary Facilities and other indirect costs during construction
50 SYSTEMS
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection | Includes a combination of new signals, replacement signals, and signal upgrades. There are also costs to add TSP to all signals. A 15% allocated contingency is used.
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications | Includes cost to add fiber within Uptown, communications to signals and station locations. Passanger information and panic buttons at the station locations is also included in this category. A 15% allocated contingency is used.
50.06 | Fare collection system and equipment | Includes ticket vending machines and validators at most station locations, except the existing busway stations and the small neighborhood stations. A 15% allocated contingency is used.
50.07 | Central Control
Construction Subtotal (10 - 50)
60 ROW, LAND, EXISTING IMPROVEMENTS
60.01 | Purchase or lease of real estate | Includes purchase of real estate for sliver takes along the route and one empty parcel in Oakland for a layover/comfort station. A 10% allocated contingency is used.
60.02 | Relocation of existing households and businesses
70 VEHICLES (number)
70.01 | Light Rail
70.02 | Heavy Rail
70.03 | Commuter Rail
70.04 | Bus | Twenty-five (25) new battery electric, articulated buses are proposed for the BRT Core service and thirty four (34) diesel buses, rebranded to match the new battery electric buses are prososed for the branches. A 1% contingency is used as pricing is based on recent quote.
70.05 | Other
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
80.01 | Project Development | Includesactual contract costs for NEPA and Preliminary Engineering after enterance into Project Development. A 5% allocated contingency is used.
80.02 | Engineering (not applicable to Small Starts)
80.03 | Project Management for Design and Construction | A cost utilizing 10% of base construction subtotal is used; a 5% allocated contingency is also included.
80.04 | Construction Administration & Management | A cost utilizing 10% of base construction subtotal is used plus $238,000 for URA management; a 5% allocated contingency is also included.
80.05 | Professional Liability and other Non-Construction Insurance | A cost utilizing 1/2 % of base construction subtotal is used; a 5% allocated contingency is also included.
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | A cost utilizing 1/2 % of base construction subtotal is used; a 5% allocated contingency is also included.
80.07 | Surveys, Testing, Investigation, Inspection | A cost utilizing 1/2 % of base construction subtotal is used; a 5% allocated contingency is also included.
80.08 | Start up
Subtotal (10 - 80)
90 UNALLOCATED CONTINGENCY |  | A 4.157% unallocated contingency is applied based on the construction base year subtotal for items 10 to 50
Subtotal (10 - 90)
100 FINANCE CHARGES
Total Project Cost (10 - 100)
Note on C8: These rows can be expanded to fit your narrative. Delete lines that are not needed.
Note on C27: For each garage, list station name, number of floors above and below grade, and number of spaces in each garage.
Note on C42: For each parking lot, list station name and number of spaces.

## Schedule
S C H E D U L E |  |  | (Rev.19, June 2017)
Urban Redevelopment Authority of Pittsburgh (URA) | Today's Date |  | 2019-03-12 11:30
Downtown-Uptown-Oakland-East End Bus Rapid Transit | Yr of Base Year $ |  | 2018
Application to enter the President's FY2020 Budget | Yr of Revenue Ops |  | 2021
Insert comments, notes, etc. |  | Start Date | End Date | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036
Project Development |  | 2017-05-31 | 2019-11-01
Design
Develop cost estimate, schedule, ridership forecast
Conduct reviews
Develop NEPA document (DCE/EA/FEIS) and receive determination (CE/FONSI/ROD)
Develop the contract documents for the Build Alternative
Acquire real estate; relocate households and businesses
Submit request / receive FTA approval for SSGA
Issue requests for bids, make awards of construction contracts
Construction |  | 2019-11-01 | 2021-11-01
Construct fixed infrastructure
Insert Contract Package Number and Description (i.e. Guideway, Stations, Systems, etc.)
Insert Contract Package Number and Description (i.e. Guideway, Stations, Systems, etc.)
Finalize real estate acquisitions and relocations
Acquire and test vehicles
Revenue Ops / Closeout of Project |  | 2021-11-01 | 2022-09-01
Revenue Service Date |  | 2021-11-01
Revenue Operations
Fulfillment of the Small Starts funding commitment
Completion of project close-out, resolution of claims
Note on E6: Delete years that are not applicable.
Note on C7: On this Schedule and on the Inflation Worksheet, indicate the start of PD with the date of FTA's letter granting entry into PD. Delete any rows that are not needed.

## BUILD Annualized
A N N U A L I Z E D C O S T - B U I L D A L T E R N A T I V E (Current Year) | [9 empty] | (Rev.19, June 2017)
Urban Redevelopment Authority of Pittsburgh (URA) | [7 empty] | Today's Date |  | 2019-03-12 11:30
Downtown-Uptown-Oakland-East End Bus Rapid Transit | [7 empty] | Yr of Base Year $ |  | 2018
Application to enter the President's FY2020 Budget | [7 empty] | Yr of Revenue Ops |  | 2021
|  | Quantity | Total Base Year Dollars (X000) | Cat. 80 Prof. Svc. spread proportionally over Cats. 10 - 50 (X000) | Spread Cat. 90 Unalloc. Cont. according to perceived risks (X000) | Revised Total Base Year Dollars (X000) | Federal Share of Base Year Dollars (based on 64.5 percent Federal funding share) | Years of Useful Life | Annualization Factor (based on 2% rate) [.02/1 - (1.02)^-no. yrs] | Annualized Federal Share (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 10.45 | 25521432.9987 | 5867039.8953 | 922539.2172 | 32311012.1112 | 20851884.3536 |  |  | 931035.0161
10.01 | Guideway: At-grade exclusive right-of-way | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0.021837 | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 10.45 | 25521432.9987 | 5867039.8953 | 922539.2172 | 32311012.1112 | 20851884.3536 | 30 | 0.04465 | 931035.0161
10.03 | Guideway: At-grade in mixed traffic | 0 | 0 | 0 |  | 0 | 0 | 20 | 0.061157 | 0
10.04 | Guideway: Aerial structure | 0 | 0 | 0 |  | 0 | 0 | 80 | 0.025161 | 0
10.05 | Guideway: Built-up fill | 0 | 0 | 0 |  | 0 | 0 | 80 | 0.025161 | 0
10.06 | Guideway: Underground cut & cover | 0 | 0 | 0 |  | 0 | 0 | 125 | 0.021837 | 0
10.07 | Guideway: Underground tunnel | 0 | 0 | 0 |  | 0 | 0 | 125 | 0.021837 | 0
10.08 | Guideway: Retained cut or fill | 0 | 0 | 0 |  | 0 | 0 | 125 | 0.021837 | 0
10.09 | Track: Direct fixation |  | 0 | 0 |  | 0 | 0 | 30 | 0.04465 | 0
10.1 | Track: Embedded |  | 0 | 0 |  | 0 | 0 | 20 | 0.061157 | 0
10.11 | Track: Ballasted |  | 0 | 0 |  | 0 | 0 | 35 | 0.040002 | 0
10.12 | Track: Special (switches, turnouts) |  | 0 | 0 |  | 0 | 0 | 30 | 0.04465 | 0
10.13 | Track: Vibration and noise dampening |  | 0 | 0 |  | 0 | 0 | 30 | 0.04465 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 44 | 15042730.25 | 3458124.7266 | 543758.9884 | 19044613.965 | 12290425.524 |  |  | 327756.7483
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 44 | 15042730.25 | 3458124.7266 | 543758.9884 | 19044613.965 | 12290425.524 | 70 | 0.026668 | 327756.7483
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 0 | 70 | 0.026668 | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 0 | 125 | 0.021837 | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 | 0 | 0 |  | 0 | 0 | 70 | 0.026668 | 0
20.05 | Joint development |  | 0 | 0 |  | 0 | 0 | 70 | 0.026668 | 0
20.06 | Automobile parking multi-story structure |  | 0 | 0 |  | 0 | 0 | 50 | 0.031823 | 0
20.07 | Elevators, escalators |  | 0 | 0 |  | 0 | 0 | 30 | 0.04465 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  |  | 9582681.4281 | 2202931.7181 | 346391.1852 | 12132004.3314 | 7829378.7401 |  |  | 249155.9615
30.01 | Administration Building: Office, sales, storage, revenue counting |  | 0 | 0 |  | 0 | 0 | 50 | 0.031823 | 0
30.02 | Light Maintenance Facility |  | 9582681.4281 | 2202931.7181 | 346391.1852 | 12132004.3314 | 7829378.7401 | 50 | 0.031823 | 249155.9615
30.03 | Heavy Maintenance Facility |  | 0 | 0 |  | 0 | 0 | 50 | 0.031823 | 0
30.04 | Storage or Maintenance of Way Building |  | 0 | 0 |  | 0 | 0 | 50 | 0.031823 | 0
30.05 | Yard and Yard Track |  | 0 | 0 |  | 0 | 0 | 80 | 0.025161 | 0
40 SITEWORK & SPECIAL CONDITIONS |  |  | 16953712.5032 | 3897434.2716 | 612836.4604 | 21463983.2352 | 13851763.4374 |  |  | 673851.967
40.01 | Demolition, Clearing, Earthwork |  | 300071.5033 | 68982.4698 | 10846.8725 | 379900.8456 | 245168.6896 | 125 | 0.021837 | 5353.8193
40.02 | Site Utilities, Utility Relocation |  | 5041943.3918 | 1159076.1001 | 182254.2845 | 6383273.7764 | 4119440.3359 | 125 | 0.021837 | 89957.4049
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  | 51750 | 11896.6405 | 1870.6397 | 65517.2802 | 42281.5214 | 125 | 0.021837 | 923.3138
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 0 | 0 |  | 0 | 0 | 125 | 0.021837 | 0
40.05 | Site structures including retaining walls, sound walls |  | 0 | 0 |  | 0 | 0 | 80 | 0.025161 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 11559947.6081 | 2657479.0611 | 417864.6637 | 14635291.3329 | 9444872.8905 | 20 | 0.061157 | 577617.4291
40.07 | Automobile, bus, van accessways including roads, parking lots |  | 0 | 0 |  | 0 | 0 | 20 | 0.061157 | 0
40.08 | Temporary Facilities and other indirect costs during construction |  | 0 | 0 |  | 0 | 0 | 100 | 0.023203 | 0
50 SYSTEMS |  |  | 46297206.3047 | 10643115.3942 | 1673534.1024 | 58613855.8013 | 37826402.2952 |  |  | 1811372.0781
50.01 | Train control and signals |  | 0 | 0 | 0 | 0 | 0 | 30 | 0.04465 | 0
50.02 | Traffic signals and crossing protection |  | 28732006.2375 | 6605108.2193 | 1038593.8182 | 36375708.275 | 23475032.587 | 30 | 0.04465 | 1048158.3808
50.03 | Traction power supply: substations |  | 0 | 0 |  | 0 | 0 | 50 | 0.031823 | 0
50.04 | Traction power distribution: catenary and third rail |  | 0 | 0 |  | 0 | 0 | 30 | 0.04465 | 0
50.05 | Communications |  | 3465050.0672 | 796569.1811 | 125253.3342 | 4386872.5824 | 2831064.5129 | 20 | 0.061157 | 173138.6144
50.06 | Fare collection system and equipment |  | 14100150 | 3241437.9939 | 509686.95 | 17851274.9438 | 11520305.1954 | 25 | 0.05122 | 590075.0828
50.07 | Central Control |  | 0 | 0 |  | 0 | 0 | 30 | 0.04465 | 0
Construction Subtotal (10 - 50) |  |  | 113397763.4847 | 26068646.0058 | 4099059.9535 | 143565469.4441 | 92649854.3502 |  |  | 3993171.7709
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | 1380210.7 |  | 0 | 1380210.7 | 890717.8086 |  |  | 19450.8613
60.01 | Purchase or lease of real estate |  | 1380210.7 |  | 0 | 1380210.7 | 890717.8086 | 125 | 0.021837 | 19450.8613
60.02 | Relocation of existing households and businesses |  | 0 |  |  | 0 | 0 | 125 | 0.021837 | 0
70 VEHICLES (number) |  | 25 | 33820899.39 |  | 0 | 33820899.39 | 21826288.8326 |  |  | 2063885.0678
70.01 | Light Rail | 0 | 0 |  | 0 | 0 | 0 | 25 | 0.05122 | 0
70.02 | Heavy Rail | 0 | 0 |  |  | 0 | 0 | 25 | 0.05122 | 0
70.03 | Commuter Rail | 0 | 0 |  |  | 0 | 0 | 25 | 0.05122 | 0
70.04 | Bus | 25 | 33820899.39 |  |  | 33820899.39 | 21826288.8326 | 12 | 0.09456 | 2063885.0678
70.05 | Other | 0 | 0 |  |  | 0 | 0 | 12 | 0.09456 | 0
70.06 | Non-revenue vehicles | 0 | 0 |  |  | 0 | 0 | 12 | 0.09456 | 0
70.07 | Spare parts | 0 | 0 |  |  | 0 | 0 | 12 | 0.09456 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  |  | 26068646.0058
80.01 | Project Development |  | 2770772
80.02 | Engineering (not applicable to Small Starts) |  | 0
80.03 | Project Management for Design and Construction |  | 10353708.8399
80.04 | Construction Administration & Management |  | 10603608.8399
80.05 | Professional Liability and other Non-Construction Insurance |  | 517685.442
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 517685.442
80.07 | Surveys, Testing, Investigation, Inspection |  | 517685.442
80.08 | Start up |  | 787500
Subtotal (10 - 80) |  |  | 174667519.5805
90 UNALLOCATED CONTINGENCY |  |  | 4099059.9535
TOTAL |  |  | 178766579.5341 | 26068646.0058 | 4099059.9535 | 178766579.5341 | 115366860.9914 |  |  | 6076507.7
Note on I60: The range for buses is 12 to 18 years. Provide supporting documentation for an estimated useful life of more than 12 years.
Note on E75: E75 and F75 are double-checks

## Fund Source by Cat
F U N D I N G S O U R C E S B Y C A T E G O R Y | [11 empty] | (Rev.19, June 2017)
Urban Redevelopment Authority of Pittsburgh (URA) | [9 empty] | Today's Date |  | 2019-03-12 11:30
Downtown-Uptown-Oakland-East End Bus Rapid Transit
Application to enter the President's FY2020 Budget
| Cost |  | Funding Summary |  |  | Federal Sources |  |  |  |  | Local Sources
| YOE Cost (X000) | Double- check Total | Federal 5309 Small Starts Funds | Federal Other Funds | Local Funds | Federal 5309 Small Starts | FTA Formula Funds for Bus Procurement | ATCMTD FHWA (Smart Spine) | CMAQ (Oakland BRT Signals) | Other | FTA Formula Funds for Bus Procurement (Local Match) [Bond] | ATCMTD FHWA (Smart Spine) (Local Match) [General Funds]
[13 empty] | CMAQ (Oakland BRT Signals) (Local Match) [Sales Tax] | State Technical Assistance and Consolidated Capital Grants (BRT Pre-development) [Sales Tax] | State Capital Budget Transportation Assistance Program Authorization [Sales Tax] | Pennsylvania Department of Transportation Multimodal Transportation Fund [Bond] | Allegheny County Budget Capital (BRT Implementation, $5M/yr over 3 yrs) [General Funds} | Allegheny County Budget Capital (BRT Pre-development) [General Funds} | City of Pittsburgh, In-kind Station Improvement Program [General Funds} | Uptown/West Oakland Eco-Innovation TRID [TRID / Bond] | Pennsylvania Department of Community and Economic Development
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 27890395.7283 | 27890395.7283 | 6441817.7052 | 0 | 21448578.0231 | 6441817.7052 | [9 empty] | 15000000 | 757762.0231 |  |  | 5000000 | 690816
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 16537659.3778 | 16537659.3778 | 3776659.3778 | 0 | 12761000 | 3776659.3778 | [12 empty] | 12761000
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10534997.2213 | 10534997.2213 | 8038640.323 | 0 | 2496356.8983 | 8038640.323 | [10 empty] | 2496356.8983
40 SITEWORK & SPECIAL CONDITIONS | 18582975.4981 | 18582975.4981 | 18440653.435 | 0 | 142322.0631 | 18440653.435 | [10 empty] | 142322.0631
50 SYSTEMS | 51197289.8419 | 51197289.8419 | 24167090.3721 | 12415760 | 14614439.4698 | 24167090.3721 |  | 10850000 | 1565760 |  |  | 4650000 | 391440 |  |  |  | 9572999.4698
60 ROW, LAND, EXISTING IMPROVEMENTS | 1464265.5316 | 1464265.5316 | 756907.5479 | 0 | 707357.9837 | 756907.5479 | [10 empty] | 707357.9837
70 VEHICLES (number) | 36965083.061 | 36965083.061 | 12002334.1919 | 16000000 | 8962748.8691 | 12002334.1919 | 16000000 |  |  |  | 4000000 |  |  |  | 4385193.1453 |  | 577555.7238
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 27780993.1696 | 27780993.1696 | 21123722.8238 | 0 | 6657270.3458 | 21123722.8238 | [7 empty] | 1212258 | 3140852.5077 |  | 745645.8381 | 1558514
90 UNALLOCATED CONTINGENCY | 4546340.7881 | 4546340.7881 | 3002174.1082 | 0 | 1544166.6799 | 3002174.1082 | [8 empty] | 1544166.6799
100 FINANCE CHARGES | 0 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 195500000.2178 | 195500000.2178 | 97749999.8849 | 28415760 | 69334240.3329 | 97749999.8849 | 16000000 | 10850000 | 1565760 | 0 | 4000000 | 4650000 | 391440 | 1212258 | 9070212.3329 | 15000000 | 15000000 | 1558514 | 12761000 | 5000000 | 690816
Percentage of Total Project Cost | 100% |  | 50% | 14.53% | 35.47% | 50% | 8.184% | 5.55% | 0.8009% | 0% | 2.046% | 2.379% | 0.2002% | 0.6201% | 4.639% | 7.673% | 7.673% | 0.7972% | 6.527% | 2.558% | 0.3534%
|  |  | 50% | 50%
100%
| 8488558.903 | 9044166.6799 | 555607.777
Note on W7: Insert additional columns as required.
Note on A9: Delete rows that are not needed.

## Fund Source by Year
F U N D I N G S O U R C E S B Y Y E A R |  |  |  |  | (Rev.19, June 2017)
Urban Redevelopment Authority of Pittsburgh (URA) |  |  | Today's Date |  | 2019-03-12 11:30
Downtown-Uptown-Oakland-East End Bus Rapid Transit
Application to enter the President's FY2020 Budget
| Total, All Years |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036
Total Project Cost In YOE Dollars Below insert funding sources and amounts for each year. | 195500000.2178 | double check | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2770772 | 6712676.3465 | 24467168.3205 | 108103559.8183 | 53445823.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Federal 5309 Small Starts | 97749999.8849 | 97749999.8849 | 2020: 48874999.9425; 2021: 48874999.9425
Local | 69334240.3329 | 69334240.3329 | 2017: 2770772; 2018: 1379343.0132; 2019: 12925954.9871; 2020: 47687346.5425; 2021: 4570823.7901
Federal Other | 28415760 | 28415760 | 2018: 5333333.3333; 2019: 11541213.3333; 2020: 11541213.3333
Total Project Cost (10 - 100) | 195500000.2178 | 195500000.2178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2770772 | 6712676.3465 | 24467168.3205 | 108103559.8183 | 53445823.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on N6: The information reported below should match what is reported in the financial plan. FTA uses this data to get an understanding of future demand for Section 5309 funds. The inputs should not assume Section 5309 funding in fiscal years for which appropriations have already occurred and the project did not receive anything.

## SSGA A3T1
Table 1 - BCE by Standard Cost Category
Applicable Line Items Only |  | YOE Dollars Total (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 27890395.7283
10.01 | Guideway: At-grade exclusive right-of-way | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 27890395.7283
10.03 | Guideway: At-grade in mixed traffic | 0
10.04 | Guideway: Aerial structure | 0
10.05 | Guideway: Built-up fill | 0
10.06 | Guideway: Underground cut & cover | 0
10.07 | Guideway: Underground tunnel | 0
10.08 | Guideway: Retained cut or fill | 0
10.09 | Track: Direct fixation | 0
10.1 | Track: Embedded | 0
10.11 | Track: Ballasted | 0
10.12 | Track: Special (switches, turnouts) | 0
10.13 | Track: Vibration and noise dampening | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 16537659.3778
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 16537659.3778
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0
20.05 | Joint development | 0
20.06 | Automobile parking multi-story structure | 0
20.07 | Elevators, escalators | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 10534997.2213
30.01 | Administration Building: Office, sales, storage, revenue counting | 0
30.02 | Light Maintenance Facility | 10534997.2213
30.03 | Heavy Maintenance Facility | 0
30.04 | Storage or Maintenance of Way Building | 0
30.05 | Yard and Yard Track | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 18582975.4981
40.01 | Demolition, Clearing, Earthwork | 328908.5734
40.02 | Site Utilities, Utility Relocation | 5526477.4896
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 56723.2093
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 0
40.05 | Site structures including retaining walls, sound walls | 0
40.06 | Pedestrian / bike access and accommodation, landscaping | 12670866.2259
40.07 | Automobile, bus, van accessways including roads, parking lots | 0
40.08 | Temporary Facilities and other indirect costs during construction | 0
50 SYSTEMS |  | 51197289.8419
50.01 | Train control and signals | 0
50.02 | Traffic signals and crossing protection | 31772993.8476
50.03 | Traction power supply: substations | 0
50.04 | Traction power distribution: catenary and third rail | 0
50.05 | Communications | 3831790.0099
50.06 | Fare collection system and equipment | 15592505.9844
50.07 | Central Control | 0
Construction Subtotal (10 - 50) |  | 124743317.6675
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 1464265.5316
60.01 | Purchase or lease of real estate | 1464265.5316
60.02 | Relocation of existing households and businesses | 0
70 VEHICLES (number) |  | 36965083.061
70.01 | Light Rail | 0
70.02 | Heavy Rail | 0
70.03 | Commuter Rail | 0
70.04 | Bus | 36965083.061
70.05 | Other | 0
70.06 | Non-revenue vehicles | 0
70.07 | Spare parts | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | 27780993.1696
80.01 | Project Development | 2952773.1509
80.02 | Engineering (not applicable to Small Starts) | 0
80.03 | Project Management for Design and Construction | 11033803.3858
80.04 | Construction Administration & Management | 11300118.3371
80.05 | Professional Liability and other Non-Construction Insurance | 551690.1693
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | 551690.1693
80.07 | Surveys, Testing, Investigation, Inspection | 551690.1693
80.08 | Start up | 839227.7879
Subtotal (10 - 80) |  | 190953659.4297
90 UNALLOCATED CONTINGENCY |  | 4546340.7881
Subtotal (10 - 90) |  | 195500000.2178
100 FINANCE CHARGES |  | 0
Total Project Cost (10 - 100) |  | 195500000.2178
Note on B1: This sheet, SSGA A3T1, and the sheets that follow become Attachments to the SSGA
Note on B3: Delete rows that are not needed.

## SSGA A3T2
Table 2 - Inflated Cost to Year of Expenditure
| Base Year Dollars w/o Contingency (X000) | Base Year Dollars Allocated Contingency (X000) | Base Year Dollars TOTAL (X000) | Inflation Factor | YOE Dollars TOTAL (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 22192550.4336 | 3328882.565 | 25521432.9987 | 1.0928 | 27890395.7283
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 13080635 | 1962095.25 | 15042730.25 | 1.0994 | 16537659.3778
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 8332766.4593 | 1249914.9689 | 9582681.4281 | 1.0994 | 10534997.2213
40 SITEWORK & SPECIAL CONDITIONS | 14742358.6985 | 2211353.8048 | 16953712.5032 | 1.0961 | 18582975.4981
50 SYSTEMS | 40258440.2649 | 6038766.0397 | 46297206.3047 | 1.1058 | 51197289.8419
60 ROW, LAND, EXISTING IMPROVEMENTS | 1254737 | 125473.7 | 1380210.7 | 1.0609 | 1464265.5316
70 VEHICLES (number) | 33486039 | 334860.39 | 33820899.39 | 1.093 | 36965083.061
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 24959223.4341 | 1109422.5717 | 26068646.0058 | 1.0657 | 27780993.1696
90 UNALLOCATED CONTINGENCY |  |  | 4099059.9535 | 1.1091 | 4546340.7881
100 FINANCE CHARGES |  |  | 0 | #DIV/0! | 0
Total Project Cost (10 - 100) |  |  | 178766579.5341 | 1.0936 | 195500000.2178
Note on G3: Delete rows that are not needed.

## A3T3
Table 3 - BCE by Source of Funding
| Total Project Cost in YOE Dollars (X000) | Double Check Total (X000) | Federal 5309 Small Starts | FTA Formula Funds for Bus Procurement | ATCMTD FHWA (Smart Spine) | CMAQ (Oakland BRT Signals) | Local
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 27890395.7283 | 27199579.7283 | 6441817.7052 | 0 | 0 | 0 | 20757762.0231
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 16537659.3778 | 16537659.3778 | 3776659.3778 | 0 | 0 | 0 | 12761000
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10534997.2213 | 10534997.2213 | 8038640.323 | 0 | 0 | 0 | 2496356.8983
40 SITEWORK & SPECIAL CONDITIONS | 18582975.4981 | 18582975.4981 | 18440653.435 | 0 | 0 | 0 | 142322.0631
50 SYSTEMS | 51197289.8419 | 51197289.8419 | 24167090.3721 | 0 | 10850000 | 1565760 | 14614439.4698
60 ROW, LAND, EXISTING IMPROVEMENTS | 1464265.5316 | 1464265.5316 | 756907.5479 | 0 | 0 | 0 | 707357.9837
70 VEHICLES (number) | 36965083.061 | 36965083.061 | 12002334.1919 | 16000000 | 0 | 0 | 8962748.8691
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 27780993.1696 | 27780993.1696 | 21123722.8238 | 0 | 0 | 0 | 6657270.3458
90 UNALLOCATED CONTINGENCY | 4546340.7881 | 4546340.7881 | 3002174.1082 | 0 | 0 | 0 | 1544166.6799
100 FINANCE CHARGES | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 195500000.2178 | 194809184.2178 | 97749999.8849 | 16000000 | 10850000 | 1565760 | 68643424.3329
Sources of Federal Funding and Matching Share Ratios
| Costs Attributed to Source of Funds (X000) | Federal/ Local Matching Ratio within Source | All Federal Funds (X000) |  |  | Local Funds (X000)
Federal 5309 New Starts | 97749999.8849 | 100/0 | 97749999.8849 |  |  | 0
FTA Formula Funds for Bus Procurement | 20000000 | 80/20 | 16000000 |  |  | 4000000
ATCMTD FHWA (Smart Spine) | 15500000 | 70/30 | 10850000 |  |  | 4650000
CMAQ (Oakland BRT Signals) | 1957200 | 80/20 | 1565760 |  |  | 391440
Local Funding | 59601984.3329 | 0/100 | 0 |  |  | 59601984.3329
Total | 194809184.2178 |  | 126165759.8849 |  |  | 68643424.3329
Overall Federal Share of Project |  |  | 64.76%
New Starts Share of Project |  |  | 50%
Note on H2: Add columns as required to show all federal funding.
Note on A3: Delete rows that are not needed.
Note on A21: Add rows as needed to show all federal funding.

## A3A
Scope and Activity Description
Scope Code | ALI Code | Scope and Activity Line Item Descriptions | Qty |  | Federal 5309 Small Starts |  |  | Federal Other |  |  | Project Totals |  |  | Check Total Project Cost in YOE Dollars (X000)
|  |  |  | Total Federal % | Federal | Local | Total | Federal | Local | Total | Federal | Local | Total
14010 | 140110 | GUIDEWAY & TRACK ELEMENTS | 10.45 | 23.68% | 6441817.7052 | 20757762.0231 | 27199579.7283 | 0 | 0 | 0 | 6441817.7052 | 20757762.0231 | 27199579.7283 | 27890395.7283
14020 | 140220 | STATIONS, STOPS, TERMINALS, INTERMODAL | 44 | 22.84% | 3776659.3778 | 12761000 | 16537659.3778 | 0 | 0 | 0 | 3776659.3778 | 12761000 | 16537659.3778 | 16537659.3778
14030 | 140330 | SUPPORT FACILITIES, YARDS, SHOPS, ADMIN. BLDGS. |  | 76.3% | 8038640.323 | 2496356.8983 | 10534997.2213 | 0 | 0 | 0 | 8038640.323 | 2496356.8983 | 10534997.2213 | 10534997.2213
14040 | 140440 | SITEWORK & SPECIAL CONDITIONS |  | 99.23% | 18440653.435 | 142322.0631 | 18582975.4981 | 0 | 0 | 0 | 18440653.435 | 142322.0631 | 18582975.4981 | 18582975.4981
14050 | 140550 | SYSTEMS |  | 71.45% | 24167090.3721 | 9572999.4698 | 33740089.8419 | 12415760 | 5041440 | 17457200 | 36582850.3721 | 14614439.4698 | 51197289.8419 | 51197289.8419
14060 | 140660 | ROW, LAND, EXISTING IMPROVEMENTS |  | 51.69% | 756907.5479 | 707357.9837 | 1464265.5316 | 0 | 0 | 0 | 756907.5479 | 707357.9837 | 1464265.5316 | 1464265.5316
14070 |  | VEHICLES | 25 | 75.75% | 12002334.1919 | 4962748.8691 | 16965083.061 | 16000000 | 4000000 | 20000000 | 28002334.1919 | 8962748.8691 | 36965083.061 | 36965083.061
| 13.13.20 | Light Rail Cars
13.__.__
14080 | 140880 | PROFESSIONAL SERVICES |  | 76.04% | 21123722.8238 | 6657270.3458 | 27780993.1696 | 0 | 0 | 0 | 21123722.8238 | 6657270.3458 | 27780993.1696 | 27780993.1696
14090 | 140990 | UNALLOCATED CONTINGENCY |  | 66.03% | 3002174.1082 | 1544166.6799 | 4546340.7881 | 0 | 0 | 0 | 3002174.1082 | 1544166.6799 | 4546340.7881 | 4546340.7881
14100 | 141010 | FINANCE CHARGES |  | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) |  |  |  | 64.76% | 97749999.8849 | 59601984.3329 | 157351984.2178 | 28415760 | 9041440 | 37457200 | 126165759.8849 | 68643424.3329 | 194809184.2178 | 195500000.2178
Note on I2: Add more tri-columns as required to show all funding.
Note on C4: Delete rows that are not needed.

## A4
SCHEDULE | Start Date | End Date | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 2019-06-01 | 2020-12-31
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 2019-06-01 | 2020-12-31
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 2019-06-01 | 2020-12-31
40 SITEWORK & SPECIAL CONDITIONS | 2019-06-01 | 2020-12-31
50 SYSTEMS | 2019-06-01 | 2020-12-31
60 ROW, LAND, EXISTING IMPROVEMENTS | 2018-06-01 | 2018-12-31
70 VEHICLES (number) | 2018-06-01 | 2020-06-01
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 2017-06-01 | 2020-12-31
90 UNALLOCATED CONTINGENCY | 2018-01-01 | 2020-12-31
100 FINANCE CHARGES
Revenue Ops / Closeout of Project | 2020-12-01 | 2021-12-31
Revenue Service Date | 2020-12-01
Fulfillment of the Small Starts funding commitment |  | 2021-12-31
Completion of project close-out, resolution of claims |  | 2021-12-31
Note on A2: Delete rows that are not needed.